## Summary
Basic Information
Name of Non Attainment City |  | Dehradun
Sate/ Union Territory |  | Uttarakhand
Name of Nodal Officer at PCB/ PCC |  | Dr. Ankur Kansal
Email Id |  | ncaputtarakhnd@gmail.com
Contact Number |  | 9412992375
Date till which progress is submitted |  | 30.06.2021
Action Point Code | Sector | Total Number of Actions | Number of Actions Completed | Number of Actions Under Progress | Required funds (in Lac)
CB | CAPACITY BUILDING, MONITORING NETWORK AND SOURCE APPORTIONMENT including Salary of 01 JRF | 4 | 0 | 4 | 900
PO | PUBLIC OUTREACH | 3 | 1 | 2 | 100
RD/ C&D | ROAD DUST AND CONTRUCTION & DEMOLITION | 12 | 1 | 11 | 1965
VE | VEHICLES | 17 | 3 | 14 | 60
IP | INDUSTRIES | 1 | 0 | 1 | --
BB/DF | WASTE AND BIOMASS- DUMPING AND BURNING | 2 | 1 | 1 | --
DF | DOMESTIC FUEL | 5 | 1 | 4 | --
AQ | AIR QUALITY DATA | Data is being submitted |  |  | --
|  | Total |  |  | 3025

## Capacity Building & SA
CAPACITY BUILDING, MONITORING NETWORK AND SOURCE APPORTIONMENT
Action Point Code | Action Point | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated (in lacs) | Funds released | Funds Utilized | Additional Funds Required | Remarks
CB 1.1 | Air Quality Monitoring to be strengthened by installation of real time sensors and monitors | In progress | 03 CAAQMS | 2022-03-01 | No | _ | Number | Nil | Nil | 750 | Nil | Nil | Nil | Regional officer, UKPCB Dehradun, reported that 02 real time sensors are required for Air quality; given by CPCB. UKPCB has published Tender for procurement of 01 CAAQMS for Dehradun but presently CPCB has directed to stop ordering the CAAQMS. Hence the tender schedule I is delayed for few months.
CB 3.1, CB3.3 | Emission Inventory and Source Apportionment Study | In progress | 100% (EI & SA Study) | 2025-03-01 | No | _ | Study | Nil | Nil | 100 | Nil | Nil | Nil | For Dehradun, CPCB is requested to carry out joint study for the EI and SA study (as per proposal of CPCB).
CB 4 | Capacity building on how to strengthen air quality management for the city to be carried out for all departments that are involved in city administration | MoU signed with ARIES Nainital | Regular activity | 2022-03-01 | No | _ | Text | Nil | Nil | Nil | Nil | Nil | Nil | Workshop was organised in DIT university on 21.01.2021 for Air Quality Monitoring. and for technical assistance ARIES Nainital is engaged.
AP1 | Centre of Excellence on air quality to be set up by pooling in all technical organization in the city. The technical organization will promote and aid the city administration and UKPCB in undertaking air quality research | In progress | _ | 2025-03-01 | No | _ | Study | Nil | Nil | 50 | Nil | Nil | Nil | A Proposal is sent to Doon university, as doon university is obtained as centre of excellence on air quality.
[10 empty] | 900 | 0 | 0 | 0

## Public Outreach
PUBLIC OUTREACH & OTHER ACTIVITES
Action Point Code | Action Point | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated (in lacs ) | Funds released | Funds Utilized | Additional Funds Required | Remarks
PO1 | Public Outreach & Other activities
PO1.3 VE8 | Issue of advisory to public for prevention and control of air pollution, Vehicle fitness, maintenance and minimise use of personal vehicles etc. | Publish the Advertisement and continuous activity | Regular Activity | Regular Activity | No | Nil | Text | Nil | Nil | 50 | Nil | Nil | Nil | 1. 01 Workshops was conducted at DIT University to discuss various issues related to air pollution and its mitigations measures. 2. Board has also distributed pamphlets and posters on Do’s and Don’ts for Air Pollution Control. Also, advertisement for the awareness has been published in Daily News Papers. 3.Under the road safety program, the general public is made aware of their vehicles from time to time for maintenance, fitness certificate PUC and minimum use of private vehicles.
VE2 | A public awareness campaign will be launched to inform the public about anti-idling measures, vehicle maintenance, eco-driving, use of public transport etc. | Continuous activity | Regular Activity | Regular Activity | No | Nil | Text | Nil | Nil | 50 | Nil | Nil | Nil | 1. Conducting awareness campaigns regarding anti-idling repairing of vehicles, eco driving and public transport. 2. It has directed that police take actions against the busiest places of dehradun like Ashley hall, elora, dilaram chowk etc. and it is directed to transport department that public awareness campaign will be run regarding Anti-idling, repairing of vehicles, eco driving and public transport, and details of action will be presented in the next meeting.
PO2 | Public Grievance Redressal Portal | Completed | Completed | 2022-03-01 | No | Completed | Yes | Nil | Nil | Nil | Nil | Nil | Nil | Web based Android app for Redressal of public complaints on air pollution along with a supervisory control for the disposal of complaints has been created by UKPCB.
[10 empty] | 100 | 0 | 0 | 0

## Road Dust
ROAD DUST AND CONTRUCTION & DEMOLITION
Action Point Code | Action Point | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated (in lacs) | Funds released | Funds Utilized | Additional Funds Required | Remarks
RD1 | Road dust
RD1.14 | Roads to be regularly monitored to ensure maintenance | In Progress | _ | 2022-03-01 | No | Nil | Number | Nil | Nil | 1500 | Nil | Nil | Nil | 1. It is directed to Municipal Corporation and PWD department to complete the patch work of road according to time. 2. Darshan lal chowk road digged, from last month so it is directed to make it as soon as possible.
RD2.2 | Green buffers to be introduced on either side of traffic corridors. | In Progress | Complete plantation along the traffic corridors | 2025-03-01 | No | Nil | Percent of green cover | Nil | Nil | Nil | Nil | Nil | Nil | 1. Direction given to MDDA, Nagar Nigam make a plan for establishment of green buffers on both side of the road and present it in next meeting. 2. Direction given to PWD engineers to locate and mark the empty places near roads for green buffers and make a estimation for green buffers.
RD2.3 | Greening of open areas, schools, gardens, community places and housing societies. | Direction given to concerned department | _ | 2025-03-01 | No | Nil | Percent of green cover | Nil | Nil | Nil | Nil | Nil | Nil | Directions given to the concern departments to make proposal for greening of open areas, schools, gardens, community places and housing societies, and present it in next meeting
RD1.15 | Ensure sidewalks are present in major parts of the city for pedestrians | Direction given to concerned department | _ | 2026-03-01 | No | Nil | Length of sidewalk stretch | Nil | Nil | 120 | Nil | Nil | Nil | In meeting, dated on 22/06/2021 department are directed to carry out survey for the construction of sidewalks for pedestrians along the road inside the city and after inspecting those places the details will be presented in the next meeting.
RD1.6 | Daily Cleaning of roads by Vacuum cleaning machines | 03 vehicle mounted vaccum cleaning machine & 02 road sweeping machine | 100% cleaning of Major Roads | 2022-03-01 | No | Nil | Number | Nil | Nil | 300 | Nil | Nil | Nil | Daily Cleaning by:- 03 vehicle mounted vaccum cleaning machine (jatayu) & 02 road sweeping machine
RD2.4 | Creation of green lungs in the city through city forestation. | In Progress | _ | 2025-03-01 | No | Nil | Area | Nil | Nil | Nil | Nil | Nil | Nil | It is being done mainly by forest department and by Nagar Nigam time to time like on occasion of Harela parv & Environment day etc
C&D1 | Construction Activities
C&D1.8 | Enforcement of construction and demolition rules 2016. | Byelaws prepared | Enforcement of byelaws |  | No | Nil | Enforcement | Nil | Nil | Nil | Nil | Nil | Nil | Bylaws prepared and RFP also prepared
C&D1.4 | Water sprinkling, curtains, barriers and dust suppression unit to be used during all construction and demolition activities including covering the construction sites | In Progress | 100% cleaning of Major Roads around C&D activities | 2022-03-01 | No | Nil | Number | Nil | Nil | 45 | Nil | Nil | Nil | It has directed to MDDA, Tehsil Administration and Nagar Nigam Dehradun, that water sprinkling system is needed to control the dust generated by construction and demolition activities & installation of curtain walls around the construction site. The details of the action taken will be presented in the next meeting.
C&D1.3 | Restriction on storage of construction materials along the road. | Implemented & Continuous activity | Regular activity | 2025-03-01 | No | Nil | Text and Number both | Nil | Nil | Nil | Nil | Nil | Nil | On storage of construction materials along the road Municipal Coropration, Dehradun charges fine. Total challan of year- 2019-20:- Rs. 13,61,379/- 2020-21:- Rs. 4,92,506/-
C&D1.1 | Transportation of municipal solid wastes,construction materials and debris in covered system. | Implemented & Continuous activity | Regular activity | 2025-03-01 | No | Nil | Text and Number both | Nil | Nil | Nil | Nil | Nil | Nil | Action is being taken against the vehicles carrying municipal solid waste and debris in open vehicle, by Nagar nigam and transport department.
C&D1.1 | Ensure construction material is transported and carried in close containers. | Direction given to concerned department | Regular activity | 2025-03-01 | No | Nil | Text | Nil | Nil | Nil | Nil | Nil | Nil | Direction given to Nagar Nigam, Transport department and Traffic Police to take action against if the construction material is not transported in close container.
C&D1.5 | Identification of designated place/areas for disposal of demolition waste | Completed | Completed | 2022-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | Total 03 place designated for disposal of demolition waste: 1-Harbhajwala khasra no.85(A) / 0.438 Hector 2-Khulhaan/karanpur khasra no. 2(A) / 0.4000 Hector 3-Behind DIT, makkawala khasra no.86(A)/89 0.300 Hector
[10 empty] | 1965 | 0 | 0 | 0

## Vehicles
VEHICLES
Action Point Code | Action Point | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated (in lacs) | Funds released | Funds Utilized | Additional Funds Required | Remarks
VE1 | Improve and strengthen PUC programme
VE1.2 | A city-wide drive will be launched to check and curtail polluting vehicles | 913 vehicle were challaned | Regular activity | .. | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | 913 vehicle were challaned for not having valid pollution under control certificates.
VE1.2 | Regular checking of Vehicular emission and issue of Pollution under Control Certificate (PUC) | In progress | Regular activity | 2022-03-01 | No | Nil | Number | Nil | Nil | 60 | Nil | Nil | Nil | 1. Present numbers of PUC checking centers are113 in Dehradun City 2. Year wise details of PUC investigation of vehicle: 2019 – 2020: 347135 2020 – 2021: 227464 April 21 – June 21: 28698 3. Continuous checking is done by the Enforcement unit Dehradun. Action against the vehicles not having PUCs during the checking: 2020 - 21: 323 Jan 2021 - May2021 : 138
VE1.4 | Integration of all Pollution Checking Centers with Single web-based software for ensuring control & monitoring of polluting vehicles. Strengthening facility for enforcement regarding the vehicles involved in pollution emission.. | Completed | _ | 2022-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | 1. All the pollution detection centers operated under dehradun jurisdiction are integrated with “vahan 4.0” software. 2. 113 Authorized PUC centers in Dehradun.
VE4.1 | Checking for fuel adulteration periodically and random checking of fuel to be initiated | Direction given | _ | 2022-03-01 | No | Nil | Text | Nil | Nil | Nil | Nil | Nil | Nil | In meeting, it is directed to check adulteration in fuel from time to time and present the details of proceedings in the next meeting.
VE4.2 | Use of cleaner fuels (CNG/LPG) for commercial passenger vehicles | Completed and continuous activity | _ | 2025-03-01 | No | Nil | Text | Nil | Nil | Nil | Nil | Nil | Nil | There are total 04 CNG supply stations in Dehradun city 1. Malsi Filling station, Mussourie road, Dehradun 2. Shaktiman Filling station, Police line, Dehradun 3. Sarthak Filling station, Bhaniyawala , Dehradun 4. Sethi Top Filling station, Sahastradhara , Dehradun
VE5.1 | Prevent parking of vehicles in non-designated areas. - Determination of hotspots to launches action in phased manner. - Determine best strategy for positive outcome. - Branch out to other parts of the city | In progress | _ | 2022-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | Smart city provide designate parking area in first phase from Ghantaghar to Rajpur road.
VE6.5 | Public Transport to move to cleaner fuels such as CNG in a phased manner | In progress | _ | 2025-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | Total CNG stations in dehradun city 1. 04 CNG Outlet are there in the city. 2. 06 CNG Stations are under construction.
VE6.7 | Battery operated vehicles and E-rickshaws to be introduced. - Determination of areas that most need last mile connectivity to initiate launch. - Determine need and capacity for city. - Launch more e-rickshaws accordingly. | In progress | _ | 2022-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | There are 3366 E- Rikshaws/ Electric Vehicles Registered in Dehradun. 1.No. of E-Rikshaws (P) are 2725 2.No. of E-Rickshaws (G) are 641
VE7.2 | Better traffic management/ intelligent traffic system to be launched for monitoring and de-congestion (Smart Traffic) | In progress | _ | 2030-03-01 | No | Nil | Text | Nil | Nil | Nil | Nil | Nil | Nil | Work is in progress under smart city project.
VE7.3 | Expessway / bypass and flyovers to be built to decrease vehicular congestion | In progress | _ | 2026-03-01 | No | Nil | Text | Nil | Nil | Nil | Nil | Nil | Nil | Directions given to PWD to locate new flyovers and give description in next meeting.
VE7.4 | Plan to be prepared for widening of busy roads and de- congestion of traffic. | In progress | _ | 2025-03-01 | No | Nil | Text | Nil | Nil | Nil | Nil | Nil | Nil | Directions given to the concern department to enquire the intelligent traffic system for better traffic and put traffic lights properly in cross roads.
PO1.3 VE8 | Issue of advisory to public for prevention and control of air pollution, Vehicle fitness, maintenance and minimise use of personal vehicles etc (for both cities) | Continuous activity | Regular activity | 2022-03-01 | No | Nil | Text | Nil | Nil | Nil | Nil | Nil | Nil | IEC and water spray on the road by the Municipal Corporation, Dehradun
VE2 | A public awareness campaign will be launched to inform the public about anti-idling measures, vehicle maintenance, eco-driving, use of public transport etc. | Publish advertisement on newspapeer | Regular activity | 2022-03-01 | No | Nil | Text | Nil | Nil | Nil | Nil | Nil | Nil | Conducting awareness campaigns regarding anti-idling repairing of vehicles, eco driving and public transport. It has directed that police take actions against the busiest places of dehradun like Ashley hall, elora, dilaram chowk etc. and it is directed to transport department that public awareness campaign will be run regarding Anti-idling, repairing of vehicles, eco driving and public transport and details of action will be presented I the next meeting.
VE9 | Periodic calibration test of vehicular emission monitoring instrument | In progress | Regular activity | 2022-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | Periodically (Quarterly Half Yearly and Yearly) calibration test is mandatory for registered PUC Centres Around 7526 vehicles are tested in M-Fitness App and 13 vehicles are found to be unfit from Jan2021 to May2021.
VE11.1 | Monitoring on vehicle fitness of Commercial Vehicles | Completed and continuous activity | Regular activity | _ | No | Nil | URL | Nil | Nil | Nil | Nil | Nil | Nil | Presently Vehicle Fitness test doing by M-Fitness Based on app with Geo Fancing
VE11.2 | Restriction on plying and phasing out of 15 years old commercial diesel driven vehicles. | In progress | _ | .. | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | As per Section 59 of Motor vehicle Act 1988 Central Govt. can fix age limit of the vehicles. Proposal for fixation of the age limit for diesel driven vehicle in Dehradun, Uttarakhand under preparation
VE-AP1 | IR Cameras/on road remote sensing of vehicular emissions to detect polluting vehicles much like how the traffic police’s camera detects vehicle number plate. | In progress | _ | 2025-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | Direction given to transport department and traffic police to do proceding regarding IR cameras and present the details in next meeting.
[10 empty] | 60 | 0 | 0 | 0

## Industries
Industries
IP1 | Industrial air pollution control | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated | Funds released | Funds Utilized | Additional Funds Required | Remarks
IP1.1 | Industrial emission control | _ | Continuous activity | _ | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | Under compliance

## Waste Biomass & Burning
WASTE AND BIOMASS- DUMPING AND BURNING
Action Point Code | Action Point | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated | Funds released | Funds Utilized | Additional Funds Required (in Lac) | Remarks
BB1 | Biomass Burning
BB1.1 | Restriction on open burning of municipal solid waste, Biomass, plastic, horticulture waste etc | Completed and Continuous activity | Regular activity | 2025-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | Challan/Notice issused by Municipal Corporation, Dehradun for the restriction of open burning of MSW. Year wise challan detail - Year : No. of challan : Amount 2019 - 20 : 792 : 10,82,300/- 2020 - 21 : 236 : 1,63,200/- 2021 - 22 : 27 : 8,650/-
BB1.7 | Immediate lifting of solid wastes generated from de-silting and cleaning of municipal drains for its disposal. | In progress | No Burning of MSW | 2022-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | Immediate action for the removal of solid wastes & cleaning of municipal drains will be taken by Nagar Nigam.

## Domestic Fuel
DOMESTIC FUEL
Action Point Code | Action Point | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated | Funds released | Funds Utilized | Additional Funds Required (in Lac) | Remarks
BB1 | Domestic fuel
DF 1.1 | Replacement of Wood which is used as Domestic Fuel | Completed | _ | 2025-03-01 | No | Nil | Text | Nil | Nil | Nil | Nil | Nil | Nil | It is directed to use cleaner fuel instead of wood
DF 1.9 | Ensuring promotion & use of cleaner fuel for commercial purposes like local Dhaba/eateries | In progress | _ | 2025-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | By the cleaning inspector of Nagar Nigam survey of all the Dhabas / Hotels / Eateries is going on to ensure the usage of cleaner fuel for their commercial purposes.
AP1.5 | Removal of Open DG sets | In progress | Compliance of DG Sets | 2025-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | It is informed by Regional officer Dehradun, that report will be submitted after conducting a joint inspection and removal of Retrofitted Emission Control System for DG sets with 800 KW or more capacity by Nagar Nigam Dehradun and Industries Department. It was directed that action will be taken after conducting on-site inspection of open DG sets and details to be presented in the next meeting.
DF 1.1 | Ensure 100% spread of LPG connection for cooking purposes in the city. | Direction given to respective authority | _ | 2022-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | Direction given to tehsil administration for 100% spread of LPG proceedings will be done.
AP1.4 | Compliance of guidelines on D.G. sets regarding use of retrofitted emission control system (PM captured efficiency 70%) capacity equal to or above 800 KW (for both cities) | In progress | Compliance of DG Sets | 2022-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | It is informed by Regional officer, UKPCB, Dehradun, that report will be submitted after conducting a joint inspection of Retrofitted Emission Control System for DG sets with 800 KW or more capacity by Nagar Nigam Dehradun and Industries Department

## Air Quality data
AIR QUALITY DATA
Action Code | Action Point | January | February | March | April | May | June | July | August | September | October | November | December | Attachment | Attachment Contents
AQ1.1 | Monthly averages for PM2.5 (In µg/m3) 2021 | January: 96.6667; February: 96.3467; March: 101.0767; April: 98.05; May: 68.87; June: 71.79 | NA | NA
AQ1.2 | Monthly averages for PM10 (In µg/m3) 2021 | January: 169.4733; February: 174.1233; March: 187.8133; April: 193.7267; May: 116.8733; June: 127.0167 | NA | NA
AQ1.3 | Monthly averages for SO2 (In µg/m3) 2021 | January: 23.9933; February: 23.8833; March: 23.1033; April: 22.0733; May: 18.7433; June: 20.8133 | NA | NA
AQ1.4 | Monthly averages for NO2 (In µg/m3) 2021 | January: 28.23; February: 28.2933; March: 27.6033; April: 27.35; May: 22.9533; June: 23.65 | NA | NA
AQ1.5 | Annual averages for PM2.5 (In µg/m3), (Jan-Dec 2020) | January: 78.63 | NA | NA
AQ1.6 | Annual averages for PM10 (In µg/m3) (Jan-Dec 2020) | January: 120.36 | NA | NA
AQ1.7 | Annual averages for SO2 (In µg/m3) (Jan-Dec 2020) | January: 21.4 | NA | NA
AQ1.8 | Annual averages for NO2 (In µg/m3) (Jan-Dec 2020) | January: 24.63 | NA | NA
AQ1.9 | Monthly Meterological Data 2021 | January: Nil; February: Nil; March: Nil; April: Nil; May: Nil; June: Nil | NA | NA

## Sheet3
152.015 | 154.275 | 151.94 | 146.28 | 136.67 | 144.065
117.86 | 117.04 | 116.26 | 110.4 | 55.745 | 66.82
105.92 | 109.485 | 108.585 | 102.495 | 106.035 | 107.845
22.085 | 23.13 | 23.465 | 22.85 | 19.875 | 20.545
78.63
120.36
21.4
24.63