## Summary
Basic Information
Name of Non Attainment City |  | Dehradun
Sate/ Union Territory |  | Uttarakhand
Name of Nodal Officer at PCB/ PCC |  | Dr. Ankur Kansal
Email Id |  | ncaputtarakhnd@gmail.com
Contact Number |  | 9412992375
Date till which progress is submitted |  | 31.12.2021
Action Point Code | Sector | Total Number of Actions | Number of Actions Completed | Number of Actions Under Progress | Required funds (in Lac)
CB | CAPACITY BUILDING, MONITORING NETWORK AND SOURCE APPORTIONMENT including Salary of 01 JRF | 4 | 1 | 3 | 900
PO | PUBLIC OUTREACH | 3 | 1 | 2 | 100
RD/ C&D | ROAD DUST AND CONTRUCTION & DEMOLITION | 13 | 2 | 11 | 1965
VE | VEHICLES | 17 | 3 | 14 | 60
IP | INDUSTRIES | 1 | 0 | 1 | --
BB/DF | WASTE AND BIOMASS- DUMPING AND BURNING | 1 | 1 | 0 | --
DF | DOMESTIC FUEL | 5 | 1 | 4 | --
AQ | AIR QUALITY DATA | Data is being submitted |  |  | --
|  | Total |  |  | 3025

## Capacity Building & SA
CAPACITY BUILDING, MONITORING NETWORK AND SOURCE APPORTIONMENT
Action Point Code | Action Point | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated (in lacs) | Funds released | Funds Utilized | Additional Funds Required | Remarks
CB 1.1 | Air Quality Monitoring to be strengthened by installation of real time sensors and monitors | In progress | 03 CAAQMS | 2022-03-01 | No | _ | Number | Nil | Nil | 750 | 25 | 24.22 | 725 | Regional officer, UKPCB Dehradun, reported that 03 real time sensors are required for Air quality; given by CPCB. An agreement has been signed between Doon University and Uttarakhand pollution control board regarding establishment of CAAQMS station for Dehradun city and Rs. 24.22 lakh fund has been disbursed on 09.12.2021. The CAAQMS station is operationalize from jan 15. 2022.
CB 3.1, CB3.3 | Emission Inventory and Source Apportionment Study | In progress | 100% (SA, CC & EI Study) | 2025-03-01 | No | _ | Study | Nil | Nil | 100 | Nil | Nil | Nil | For Dehradun city, we are on a final MoU agreement stage with Institute of Environment and Sustainable Development (IESD) BHU, Varanasi for carrying out "Source approtionment, Carrying Capacity and Emission Inventory study".
CB 4 | Capacity building on how to strengthen air quality management for the city to be carried out for all departments that are involved in city administration | MoU signed with ARIES Nainital | Regular activity | 2022-03-01 | No | _ | Text | Nil | Nil | Nil | Nil | Nil | Nil | Workshop was organised in DIT university on 21.01.2021 for Air Quality Monitoring. and for technical assistance ARIES Nainital is engaged. A training program of dynamic NCAP portal organized through virtual conference by Head office, UKPCB to the different departments like District Administration Department, Urban Development Directorate and their Local Bodies, Transport Department, Regional Office Dehradun
AP1 | Centre of Excellence on air quality to be set up by pooling in all technical organization in the city. The technical organization will promote and aid the city administration and UKPCB in undertaking air quality research | Implemented | _ | 2025-03-01 | No | _ | Study | Nil | Nil | 50 | Nil | Nil | Nil | MOU is signed between Doon University and UKPCB for Centre of Excellence. The conference is proposed for the month of March 2022 in Doon University.
[10 empty] | 900 | 25 | 24.22 | 875

## Public Outreach
PUBLIC OUTREACH & OTHER ACTIVITES
Action Point Code | Action Point | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated (in lacs ) | Funds released | Funds Utilized | Additional Funds Required | Remarks
PO1 | Public Outreach & Other activities
PO1.3 VE8 | Issue of advisory to public for prevention and control of air pollution, Vehicle fitness, maintenance and minimise use of personal vehicles etc. | Publish the Advertisement and continuous activity | Regular Activity | Regular Activity | No | Nil | Text | Nil | Nil | 50 | Nil | Nil | Nil | 1. 01 Workshops was conducted at DIT University to discuss various issues related to air pollution and its mitigations measures. 2. Board has also distributed pamphlets and posters on Do’s and Don’ts for Air Pollution Control. Also, advertisement for the awareness has been published in Daily News Papers. 3. Under the road safety program, the general public is made aware of their vehicles from time to time for maintenance, fitness certificate PUC and minimum use of private vehicles. 4. A training program of dynamic NCAP portal organized through virtual conference by Head office, UKPCB to the different departments like District Administration Department, Urban Development Directorate and their Local Bodies, Transport Department, Regional Office Dehradun. 5. Officials from Region office interacted with students & local people, aware them about pollution control measure adopted in daily routing activities and distributed pamphlets and leaflets in offices, Hotels, Automobile workshops, Shops, Bus stand & Auto stand in Dehradun city on "International Day of Clean Air for Blue Skies". 6. Board has organized online essay competition on “International day for the preservation of the Ozone layer”: Global Warming and Climate Change.
VE2 | A public awareness campaign will be launched to inform the public about anti-idling measures, vehicle maintenance, eco-driving, use of public transport etc. | Continuous activity | Regular Activity | Regular Activity | No | Nil | Text | Nil | Nil | 50 | Nil | Nil | Nil | 1. Conducting awareness campaigns regarding anti-idling repairing of vehicles, eco driving and public transport. 2. It has directed that police take actions against the busiest places of dehradun like Ashley hall, elora, dilaram chowk etc. and it is directed to transport department that public awareness campaign will be run regarding Anti-idling, repairing of vehicles, eco driving and public transport, and details of action will be presented in the next meeting. 3. Officials from Region office interacted with students, aware them about pollution control measure adopted in daily routing activities and distributed pamphlets and leaflets in schools on International Day of Clean Air for Blue Skies. 4. Board has organized online essay competition on “International day for the preservation of the Ozone layer”: Global Warming and Climate Change.
PO2 | Public Grievance Redressal Portal | Completed | Completed | 2022-03-01 | No | Completed | Yes | Nil | Nil | Nil | Nil | Nil | Nil | Web based Android app for Redressal of public complaints on air pollution along with a supervisory control for the disposal of complaints has been created by UKPCB. As of now total 12 complaints has been recieved for Dehradun city, out of which 09 is resolved and 03 is pending.
[10 empty] | 100 | 0 | 0 | 0

## Road Dust
ROAD DUST AND CONTRUCTION & DEMOLITION
Action Point Code | Action Point | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated (in lacs) | Funds released | Funds Utilized | Additional Funds Required | Remarks
RD1 | Road dust
RD 1.1 | Immediate lifting of solid wastes generated from de-silting and cleaning of municipal drains for its disposal. | Regular activity | No Burning of MSW | 2022-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | Compliance is being done by Municipal Corporation, Dehradun for removal of solid wastes & cleaning of municipal drains.
RD1.2 | Roads to be regularly monitored to ensure maintenance | Regular activity | _ | 2022-03-01 | No | Nil | Number | Nil | Nil | 1500 | 100 | 100 | 1380 | 1. It is directed to Municipal Corporation and PWD department to complete the patch work of road according to time. 2. Darshan lal chowk road digged, from last month so it os directed to make it as soon as possible.
RD2.2 | Green buffers to be introduced on either side of traffic corridors. | In Progress | Complete plantation along the traffic corridors | 2025-03-01 | No | Nil | Percent of green cover | Nil | Nil | Nil | Nil | Nil | Nil | 1. Direction given to MDDA, Nagar Nigam make a plan for establishment of green buffers on both side of the road and present it in next meeting. 2. Direction given to PWD engineers to locate and mark the empty places near roads for green buffers and make a estimation for green buffers.
RD2.3 | Greening of open areas, schools, gardens, community places and housing societies. | Direction given to concerned department | _ | 2025-03-01 | No | Nil | Percent of green cover | Nil | Nil | Nil | Nil | Nil | Nil | Parade ground is “The oldest ground in the dehradun” located hardly 500 mtrs from the clock tower, lavishly sprawling and snuggled in the heart of the city. Greening is being done in this parade ground. It is one of the most happening places of the dehradun that hosts many mega events time to time. In this project about 58% of the work is completed till 31.12.2021. Directions is also given to the concern departments to make proposal for greening of open areas, schools, gardens, community places and housing societies, and present it in next meeting
RD1.15 | Ensure sidewalks are present in major parts of the city for pedestrians | Direction given to concerned department | _ | 2026-03-01 | No | Nil | Length of sidewalk stretch | Nil | Nil | 120 | 30 | 24 | 90 | The CITIIS is “Child Friendly Doon” project and a unique initiative envisioned by DSCL to tackle the challenges of urban mobility and put children at the center stage of city planning, design and implementation. The project is well positioned to complement the city’s smart city proposal within the ABD area. Topography survey of all 07 streches is ongoing. Execution will be started after code of conduct. Preparing the EOI (expression of interest) for tender process of tree plantation ion the various roads in Dehradun city. In meeting, dated on 22/06/2021 department are directed to carry out survey for the construction of sidewalks for pedestrians along the road inside the city and after inspecting those places the details will be presented in the next meeting.
RD1.6 | Daily Cleaning of roads by Vacuum cleaning machines | 03 vehicle mounted vaccum cleaning machine & 02 road sweeping machine | 100% cleaning of Major Roads | 2022-03-01 | No | Nil | Number | Nil | Nil | 300 | 75 | 75 | 225 | Daily Cleaning by:- 03 vehicle mounted vaccum cleaning machine (jatayu) & 02 road sweeping machine
RD2.4 | Creation of green lungs in the city through city forestation. | In Progress | _ | 2025-03-01 | No | Nil | Area | Nil | Nil | Nil | Nil | Nil | Nil | DSCL has a proposal to plant trees along the major roads (where possible) along the footpath or median to tree plantation on roads will be reducing the carbon emission, help to produce more oxygen and provide a greener view of the city. It will help in creating the similarity uniqueness to the roads of city. Improve the green cover and also create an identity, similar to the line of International cities. It is also done by forest department and Nagar Nigam time to time like on occasion of Harela parv & Environment day etc.
C&D1 | Construction Activities
C&D1.8 | Enforcement of construction and demolition rules 2016. | Implemented | Enforcement of byelaws |  | No | Nil | Enforcement | Nil | Nil | Nil | Nil | Nil | Nil | Bylaws prepared and RFP also prepared
C&D1.4 | Water sprinkling, curtains, barriers and dust suppression unit to be used during all construction and demolition activities including covering the construction sites | In Progress | 100% cleaning of Major Roads around C&D activities | 2022-03-01 | No | Nil | Number | Nil | Nil | 45 | 20 | 18 | 25 | It has directed to MDDA, Tehsil Administration and Nagar Nigam Dehradun, that water sprinkling system is needed to control the dust generated by construction and demolition activities & installation of curtain walls around the construction site. The details of the action taken will be presented in the next quarter.
C&D1.3 | Restriction on storage of construction materials along the road. | Implemented & Continuous activity | Regular activity | 2025-03-01 | No | Nil | Text and Number both | Nil | Nil | Nil | Nil | Nil | Nil | On storage of construction materials along the road Municipal Corporation, Dehradun charge fine Total challan of year- 2019-20:- Rs 13,61,379/- 2020-2021:- Rs. 4,92,506/- Total challan of Previous 03 months: Month Total challan Amount Month : Challans : Amount October : 09 : 49,905/- November : 06 : 8,800/- December : 13 : 1,05,137/-
C&D1.1 | Transportation of municipal solid wastes,construction materials and debris in covered system. | Implemented & Continuous activity | Regular activity | 2025-03-01 | No | Nil | Text and Number both | Nil | Nil | Nil | Nil | Nil | Nil | Action is being taken against the vehicles carrying municipal solid waste and debris in open vehicle by Nagar nigam and transport department. There are 103 vehicles challaned for not covered goods during 01.04.21-30.09.21
C&D1.1 | Ensure construction material is transported and carried in close containers. | Implemented and directions given to concerned department | Regular activity | 2025-03-01 | No | Nil | Text | Nil | Nil | Nil | Nil | Nil | Nil | Complied with action point. Direction given to Nagar Nigam, Transport department and Traffic Police to take action against if the construction material is not transported in close container.
C&D1.5 | Identification of designated place/areas for disposal of demolition waste | Completed | Completed | 2022-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | Total 03 place designated for disposal of demolition waste: 1-Harbhajwala khasra no.85(A) / 0.438 Hector 2-Khulhaan/karanpur khasra no. 2(A) / 0.4000 Hector 3-Behind DIT, makkawala khasra no.86(A)/89 0.300 Hector
[10 empty] | 1965 | 225 | 217 | 1740

## Vehicles
VEHICLES
Action Point Code | Action Point | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated (in lacs) | Funds released | Funds Utilized | Additional Funds Required | Remarks
VE1 | Improve and strengthen PUC programme
VE1.2 | A city-wide drive will be launched to check and curtail polluting vehicles | 903 vehicle were challaned | Regular activity | .. | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | During checking in 2021-22 upto 31.12.2021, 903 vehicle were challaned for not having valid pollution under control certificates.
VE1.2 | Regular checking of Vehicular emission and issue of Pollution under Control Certificate (PUC) | In progress | Regular activity | 2022-03-01 | No | Nil | Number | Nil | Nil | 30 | 20 | Nil | 10 | 1. Present numbers of PUC checking centres are113 in Dehradun City as on 31.12.2021. 2. Year wise details of PUC investigation of vehicle Year Issued PUC 2019 – 2020: 347135 2020 – 2021: 227464 April 21 – June 21: 28698 July21-September21: 61747 October21-December21: 53667 3. Continuous checking is done by the Enforcement unit Dehradun. Action against the vehicles not having PUCs during the checking: 2019 - 20: 783 2020-2021: 551 2021-2022: 903 Total: 2237 July 21-September 21: 486 October 21-December 21: 342
VE1.4 | Integration of all Pollution Checking Centers with Single web-based software for ensuring control & monitoring of polluting vehicles. Strengthening facility for enforcement regarding the vehicles involved in pollution emission.. | Completed | _ | 2022-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | 1. All the pollution detection centers operated under dehradun jurisdiction are integrated with “vahan 4.0” software. 2. Present numbers of PUC checking centres are113 in Dehradun City as on 31.12.2021.
VE4.1 | Checking for fuel adulteration periodically and random checking of fuel to be initiated | Direction given | _ | 2022-03-01 | No | Nil | Text | Nil | Nil | Nil | Nil | Nil | Nil | In meeting, it is directed to check adulteration in fuel from time to time and present the details of proceedings in the next meeting.
VE4.2 | Use of cleaner fuels (CNG/LPG) for commercial passenger vehicles | Completed and continuous activity | _ | 2025-03-01 | No | Nil | Text | Nil | Nil | Nil | Nil | Nil | Nil | There are total 04 operational CNG supply stations in Dehradun city: 1. Malsi Filling station, Mussourie road, Dehradun 2. Shaktiman Filling station, Police line, Dehradun 3. Sarthak Filling station, Bhaniyawala , Dehradun 4. Sethi Top Filling station, Sahastradhara , Dehradun There are 06 CNG stations under installation which are mentioned below: 1. Humara Debu Filling Station, shimla byepass road Dehradun. 2. Shree Krishna Filling Station suddhowala Dehradun. 3. Despal Singh kohli Filling Station Mohbbewala Dehradun 4. Surjan singh, Filling Station Saharanpur dehradun. 5. GAIL Gas Filling Station, Transport nagar, Dehradun 6. GAIL. Gas Filling Station, ISBT Dehradun.
VE5.1 | Prevent parking of vehicles in non-designated areas. - Determination of hotspots to launches action in phased manner. - Determine best strategy for positive outcome. - Branch out to other parts of the city | In progress | _ | 2022-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | Smart city is providing designated parking area in first phase from Ghantaghar to Rajpur road (29 km).
VE6.5 | Public Transport to move to cleaner fuels such as CNG in a phased manner | In progress | _ | 2025-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | Total CNG stations in dehradun city 1. 04 CNG Outlet are there in the city. 2. 06 CNG Stations are under installtion.
VE6.7 | Battery operated vehicles and E-rickshaws to be introduced. - Determination of areas that most need last mile connectivity to initiate launch. - Determine need and capacity for city. - Launch more e-rickshaws accordingly. | In progress | _ | 2022-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | There are 3824 E- Rikshaws/ Electric Vehicles Registered in Dehradun 1.No. of E-Rikshaws (P/G) 2493 2. CNG: 3824 3. LPG: 1331 4. Electric Vehicle: 606
VE7.2 | Better traffic management/ intelligent traffic system to be launched for monitoring and de-congestion (Smart Traffic) | In progress | _ | 2030-03-01 | No | Nil | Text | Nil | Nil | Nil | Nil | Nil | Nil | Directions given to the concern department to enquire the intelligent traffic system for better traffic and put traffic lights properly in cross roads. As per smart city limited, Total funds received from MoHUA, GOI is consolidated 247.5 Cr on 18/2/21 for all the projects. They do not get funds for each project separately.
VE7.3 | Expessway / bypass and flyovers to be built to decrease vehicular congestion | In progress | _ | 2026-03-01 | No | Nil | Text | Nil | Nil | Nil | Nil | Nil | Nil | Directions given to PWD to locate new flyovers and give description in next meeting.
VE7.4 | Plan to be prepared for widening of busy roads and de-congestion of traffic. | In progress | _ | 2025-03-01 | No | Nil | Text | Nil | Nil | Nil | Nil | Nil | Nil | Roads to be modeled as Smart Roads are - Phase I 1. Haridwar Road Prince Chowk to Araghar Road (1.5 Km) 2. EC Road - Araghar Road to Behl Chowk (3.0 Km) Phase II 3. Rajpur Road Dilaram Chowk to Clock Tower (2.0 Km) 4. Chakrata Road Clock Tower to Kishan Nagar Chowk (2.0 Km) These roads are some of the key arteries in the city. Improvements to these roads effectively will bring in change in face of the and possibly leads to the all roads in the city converted to these standard over time. Physical p[rogress on this project is 28% completed as on 31.12.2021.
PO1.3 VE8 | Issue of advisory to public for prevention and control of air pollution, Vehicle fitness, maintenance and minimise use of personal vehicles etc. | Continuous activity | Regular activity | 2022-03-01 | No | Nil | Text | Nil | Nil | Nil | Nil | Nil | Nil | 1. Conducting awareness campaigns regarding anti-idling repairing of vehicles, eco driving and public transport. 2. IEC and water spray on the road by the Municipal Corporation, Dehradun
VE2 | A public awareness campaign will be launched to inform the public about anti-idling measures, vehicle maintenance, eco-driving, use of public transport etc. | Publish advertisement on newspapeer | Regular activity | 2022-03-01 | No | Nil | Text | Nil | Nil | Nil | Nil | Nil | Nil | Conducting awareness campaigns regarding anti-idling repairing of vehicles, eco driving and public transport. It has directed that police take actions against the busiest places of dehradun like Ashley hall, elora, dilaram chowk etc. and it is directed to transport department that public awareness campaign will be run regarding Anti-idling, repairing of vehicles, eco driving and public transport and details of action will be presented I the next meeting. An awareness program conducted during 18-Jan21 to 17-Feb21 regarding vehicular pollution.
VE9 | Periodic calibration test of vehicular emission monitoring instrument | In progress | Regular activity | 2022-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | Periodically (Quarterly Half Yearly and Yearly) calibration test is mandatory for registered PUC Centres. No. of Periodic Calibration in year 2021: 62 centers.
VE11.1 | Monitoring on vehicle fitness of Commercial Vehicles | Completed and continuous activity | Regular activity | _ | No | Nil | URL | Nil | Nil | Nil | Nil | Nil | Nil | Presently Vehicle Fitness test doing by M-Fitness Based on app with Geo Fancing. Around 6707 vehicles are tested in M-Fitness App and 10 vehicles are found to be unfit from Oct 2021 to Dec 2021 Year : No. of challans / Action 2019-20 : 1899 2020-2021 : 613 2021-2022 : 193 . Year wise details of fitness certificate: Year : Issued fitness certificate 2019-20: 24082 2020-2021: 10440 2021-2022: 21098
VE11.2 | Restriction on plying and phasing out of 15 years old commercial diesel driven vehicles. | In progress | _ | .. | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | As per Section 59 of Motor vehicle Act 1988 Central Govt. can fix age limit of the vehicles. Central government has issued vehicle scrap policy which will effect from March 2023. Proposal for fixation of the age limit for diesel driven vehicle in Dehradun, Uttarakhand is under preparation.
VE-AP1 | IR Cameras/on road remote sensing of vehicular emissions to detect polluting vehicles much like how the traffic police’s camera detects vehicle number plate. | In progress | _ | 2025-03-01 | No | Nil | Number | Nil | Nil | 30 | 30 | Nil | Nil | Direction given to transport department and traffic police to do proceding regarding IR cameras and proposal is awaited from transport department for funds disbursement.
[10 empty] | 60 | 50 | 0 | 10

## Industries
Industries
IP1 | Industrial air pollution control | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated | Funds released | Funds Utilized | Additional Funds Required | Remarks
IP 1 | Industrial emission control | SIIDCUL has developed guidelines for greening of industrial areas under ongoing technical cooperation with GIZ | Continuous activity | _ | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | As per the directions, SIIDCUL has intimated the regional managers to insist industries to install required air pollution abatement equipment/devices to control and manage air pollution from their respective industrial activities as per applicable parameters being issued by UKPCB through Consent to Operate (CTO). Also, in order to better manage and control air pollution in and around industrial areas, SIIDCUL has developed guidelines for greening of industrial areas under ongoing technical cooperation with GIZ and has directed the concerned Regional Managers of SIIDCUL to review the guidelines and implement the greening in industrial areas according to these guidelines now onwards. These guidelines provide guidance on the areas where plantation can be undertaken, type of trees, size of trees, landscaping/design aspects, pre-plantation preparation requirements, requirements for undertaking plantation, post plantation care etc. Implementing these guidelines will ensure air pollution control and abatement in industrial areas.

## Waste Biomass & Burning
WASTE AND BIOMASS- DUMPING AND BURNING
Action Point Code | Action Point | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated | Funds released | Funds Utilized | Additional Funds Required (in Lac) | Remarks
BB1 | Biomass Burning
BB1.1 | Restriction on open burning of municipal solid waste, Biomass, plastic, horticulture waste etc | Completed and Continuous activity | Regular activity | 2025-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | Challan/Notice issused by Municipal Corporation, Dehradun Challan detail per year- Year : Total challans : Amount 2019 : 792 : 10,82,300/- 2020 : 236 : 1,63,200/- 2021 : 1891 : 4,96,300/- Challan/Notice issued by Municipal Corporation, Dehradun Challan detail of previous 03 months- Year : Total challan : Amount October : 116 : 97.300/- November : 91 : 27,050/- December : 402 : 93.550/-

## Domestic Fuel
DOMESTIC FUEL
Action Point Code | Action Point | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated | Funds released | Funds Utilized | Additional Funds Required (in Lac) | Remarks
BB1 | Domestic fuel
DF 1.9 | Replacement of Wood which is used as Domestic Fuel | Completed | _ | 2025-03-01 | No | Nil | Text | Nil | Nil | Nil | Nil | Nil | Nil | Direction given to tehsil administration for 100% spread of LPG proceedings should be done.
DF 1.2 | Ensuring promotion & use of cleaner fuel for commercial purposes like local Dhaba/eateries | In progress | _ | 2025-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | By the cleaning inspector of Nagar Nigam survey of all the Dhabas / Hotels / Eateries is done. Total 27526 Dhabas / Hotels / Eateries are using cleaner fuel for their commercial purposes.
AP1.5 | Removal of Open DG sets | In progress | Compliance of DG Sets | 2025-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | It is informed by Regional officer Dehradun, that report will be submitted after conducting a joint inspection and removal of Retrofitted Emission Control System for DG sets with 800 KW or more capacity by Nagar Nigam Dehradun and Industries Department. It was directed that action will be taken after conducting on-site inspection of open DG sets and details to be presented in the next meeting
DF 1.1 | Ensure 100% spread of LPG connection for cooking purposes in the city. | Direction given to respective authority | _ | 2022-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | Number of commercial LPG use in restaurants and other areas in Dehradun are 27526. Direction has also given to tehsil administration for 100% spread of LPG proceedings will be done.
AP1.4 | Compliance of guidelines on D.G. sets regarding use of retrofitted emission control system (PM captured efficiency 70%) capacity equal to or above 800 KW (for both cities) | In progress | Compliance of DG Sets | 2022-03-01 | No | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | It is informed by Regional officer, UKPCB, Dehradun, that report will be submitted after conducting a joint inspection of Retrofitted Emission Control System for DG sets with 800 KW or more capacity by Nagar Nigam Dehradun and Industries Department

## Air Quality data
AIR QUALITY DATA
Action Code | Action Point | January | February | March | April | May | June | July | August | September | October | November | December | Attachment | Attachment Contents
AQ1.1 | Monthly averages for PM2.5 (In µg/m3) 2021 | 96.6667 | 96.3467 | 101.0767 | 98.05 | 68.87 | 71.79 | 75.5567 | 95.51 | 76.5333 | 87.6 | 90.77 | 155.81 | NA | NA
AQ1.2 | Monthly averages for PM10 (In µg/m3) 2021 | 169.4733 | 174.1233 | 187.8133 | 193.7267 | 116.8733 | 127.0167 | 135.4433 | 119.4567 | 105.4067 | 127.89 | 146.15 | 89.04 | NA | NA
AQ1.3 | Monthly averages for SO2 (In µg/m3) 2021 | 23.9933 | 23.8833 | 23.1033 | 22.0733 | 18.7433 | 20.8133 | 21.28 | 21.36 | 19.5767 | 20.84 | 19.88 | 20.2 | NA | NA
AQ1.4 | Monthly averages for NO2 (In µg/m3) 2021 | 28.23 | 28.2933 | 27.6033 | 27.35 | 22.9533 | 23.65 | 24.1067 | 24.3467 | 22.3 | 24.38 | 24.97 | 24.57 | NA | NA
AQ1.5 | Annual averages for PM2.5 (In µg/m3), (Jan-Dec 2021) | 87.39 | [11 empty] | NA | NA
AQ1.6 | Annual averages for PM10 (In µg/m3) (Jan-Dec 2021) | 146.6 | [11 empty] | NA | NA
AQ1.7 | Annual averages for SO2 (In µg/m3) (Jan-Dec 2021) | 21.31 | [11 empty] | NA | NA
AQ1.8 | Annual averages for NO2 (In µg/m3) (Jan-Dec 2021) | 25.22 | [11 empty] | NA | NA
AQ1.9 | Monthly Meterological Data 2021 | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | NA