## Summary
Basic Information
Name of Non Attainment City |  | Rishikesh
Sate/ Union Territory |  | Uttarakhand
Name of Nodal Officer at PCB/ PCC |  | Dr. Ankur Kansal
Email Id |  | ncaputtarakhnd@gmail.com
Contact Number |  | 9412992375
Date till which progress is submitted |  | 30.09.2021
Action Point Code | Sector | Total Number of Actions | Number of Actions Completed | Number of Actions Under Progress | Required funds (in Lac)
CB | CAPACITY BUILDING, MONITORING NETWORK AND SOURCE APPORTIONMENT including Salary of 01 JRF | 6 | 1 | 5 | 375
PO | PUBLIC OUTREACH | 5 | 3 | 2 | 50
RD/ C&D | ROAD DUST AND CONTRUCTION & DEMOLITION | 9 | -- | 9 | 218
VE | VEHICLES | 11 | 3 | 6 | 30
IP | INDUSTRIES | 4 | 4 | -- | _
BB/DF | WASTE AND BIOMASS- DUMPING AND BURNING | 3 | -- | 3 | 0
AQ | AIR QUALITY DATA | Regularly submitted |  |  | _
|  |  |  | Total | 673

## Capacity Building & SA
CAPACITY BUILDING, MONITORING NETWORK AND SOURCE APPORTIONMENT
Action Point Code | Action Point | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated | Funds released (Rs in lakh) | Funds Utilized | Additional Funds Required (Rs in Lakh) | Remarks
CB1 | Insatllation & Commissioning of Monitoring Stations
CB1.1 | CAAQMS | 0 | 1 | 2021-03-01 | No | Nil | Number | Nil | Nil | 230 | Nil | NA | 230 | UKPCB had already published Tender for procurement of 01 CAAQMS for Rishikesh city and now we are in a process to open their financial bid after approval of higher authority.
CB1.2 | Manual Stations | 3 | 3 | 2021-03-01 | No | Nil | Number | Nil | Nil | 25 | 6 | 5.8 | 19 | Already 02 Monitoring station is in operation at Rishikesh. Equipment for operating 01 more manual stations have been installed and will be functional very soon.
CB2 | Air Quality Forecasting | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
CB3 | Assessment of sources
CB3.1 | Emission Inventory | In progress |  | 2023-03-01 |  |  | Study | Nil | Nil | 40 | Nil | NA | 40 | SA and Emission Inventory has been awarded to TERI
CB3.2 | Emission tracking system | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
CB3.3 | Source Apportionment Study | In progress |  | 2023-03-01 |  |  | Study | Nil | Nil | 40 | Nil | NA | 40 | SA and Emission Inventory has been awarded to TERI
CB3.4 | Health Impact Studies | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
CB3.5 | Exposure Impact Studies | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
CB4 | Training & Capacity Building
CB4.1 | Training & skill development of public officals | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | 5 | 0.5 | 0.41 | 4.5 | Organized workshop for city specific stakeholders in September 2019. A training program of dynamic NCAP portal organized through virtual conference by Head office, UKPCB to the different departments like District Administration Department, Urban Development Directorate and their Local Bodies, Transport Department, Regional Office Kashipur.
CB4.2 | Infrastructure development (Laboratory/ AQM Cell | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | 25 | 13.5 | 5.45 | 11.5 | AQM cell has been created
CB4.3 | Enforcement Units | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Not incorporated in Action Plan
CB5 | Emergency Response System | In progress |  | 2021-03-01 | Nil | Nil | Enforcement | Nil | Bieng Finalised | 10 | Nil | Nil | 10 | Emergency Response Plan has been finalised and National Disaster Authority is the nodal agency for the same.
[10 empty] | 375 | 20 | 11.66 | 355

## Public Outreach
Action Point Code | Action Point | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated | Funds released | Funds Utilized | Additional Funds Required | Remarks
PUBLIC OUTREACH
PO1 | Public Outreach
PO1.1 | Daily Air Quality Public Information Dissemination System | [12 empty] | Not incorporated in Action Plan
PO1.2 | Social Media Platforms | Disigned the posters & posted on various social media platforms. | _ | _ | _ | _ | URL | _ | Details of social media platforms | Nil | Nil | Nil | Not required | Twitter @Uttarakhanpcb
PO1.3 | Issue public advisory for prevention and control of air polltuion | Publish the Advertisement | _ | _ | _ | _ | Yes | _ | Number and detail of public advisories per quarter | 30 | 30 | 0 | 0 | 1. 01 Workshops was conducted at DIT University to discuss various issues related to air pollution and its mitigations measures. 2. Board has also distributed pamphlets and posters on Do’s and Don’ts for Air Pollution Control. Also, advertisement for the awareness has been published in Daily News Papers. 3. Pamphlets are also distributed by the RTO at Schools, Colleges, Union & pollution checking centers. 4. Under the road safety program, the general public is made aware of their vehicles from time to time for maintenance, fitness certificate PUC and minimum use of private vehicles. 5. A training program of dynamic NCAP portal organized through virtual conference by Head office, UKPCB to the different departments like District Administration Department, Urban Development Directorate and their Local Bodies, Transport Department, Regional Office Kashipur, Rishikesh & Dehradun. 6. Officials from Region office interacted with students & local people, aware them about pollution control measure adopted in daily routing activities and distributed pamphlets and leaflets in offices, Hotels, Automobile workshops, Shops, Bus stand & Auto stand in rishikesh city on International Day of Clean Air for Blue Skies. 7. Board has organized online essay competition on “International day for the preservation of the Ozone layer”: Global Warming and Climate Change. 8. Raised awareness through Radio FM Jingles.
PO1.4 | Deeper public engagement and consultation (workshops/ programmes in schools/ colleges) | _ |  | 2021-03-01 |  |  | Yes |  | Number & details of public awareness events held per quarter | 20 | 20 | 0 | 0 | Officials from Region office interacted with students, aware them about pollution control measure adopted in daily routing activities and distributed pamphlets and leaflets in schools on International Day of Clean Air for Blue Skies. Board has organized online essay competition on “International day for the preservation of the Ozone layer”: Global Warming and Climate Change.
PO1.5 | Launch mobile app to update public about status of air quality | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
PO2 | Public Greivance Redressal System | Completed | 2021-03-01 | Completed |  |  | Application | [6 empty] | Web based Android app for redressal of public complaints on air pollution along with a supervisory control for the disposal of complaints has been created by UKPCB. It is in operational phase
PO2.1 | App Based System | Completed | 2021-03-01 | Completed | Nil | Nil | Enforcement | Nil | Resolving process is in progress | Nil | Nil | Nil | Nil | NCAP App for Air related issues.
PO2.2 | Helpline Number | _ | _ |  | _ | _ | No | _ | _ | _ | _ | _ | _ | Not incorporated in Action Plan
[10 empty] | 50 | 50 | 0 | 0

## Road dust & C&D
Action Point Code | Road dust | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated (in lakhs) | Funds released (in lakhs) | Funds Utilized | Additional Funds Required | Remarks
RD1 | ROAD DUST AND CONTRUCTION & DEMOLITION
RD1.1 | Immediate lifting of solid waste generated from disilting and cleaning of municipal drains for its disposal | Total waste - 60 MTD Door to Door collection- 100% ( 20 workers, 20 helpers and 20 Door to Door vehicles). |  | 2021-03-01 | Completed | Nil | Amount /Number | Nil | Nil | 99 | 99 | 0 | 0 | 1. A total of 80 MTD Waste is collected from Door-to-Door Collection. 2. ULB has achieved almost 100% Door to Door Collection of Waste. It is done by 18 workers/ helpers with 30 Door-to-Door vehicles. 3. Frequency of lifting of wastage - 3 rounds per vehicle (Morning 6:00AM to Afternoon 02:00PM). 4. A Nala Gang has been formed by Nagar Nigam Rishikesh for desilting the waste from drains.
RD1.2 | Maintain potholes free roads | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil |  | Not incorporated in Action Plan
RD1.3 | Regular cleaning of street surfaces and spraying of water to suppress dust. | Manual Sweeping: - 100% 01 tanker of Water Sprinklers |  | 2021-03-01 | Completed | Nil | Number | Nil | Nil | 9 | 9 | 0 | 0 | Presently, there is 02 Tanker for Water spraying on road. UKPCB has disbursed funds (as received from GOI under NCAP) for procurement of Water Tankers.
RD1.4 | Black-topping of unpaved road | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
RD1.5 | Minimize earth cutting from the hills to prevent dust generation. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
RD1.6 | To take appropriate action to remove road dust/silt regularly by using mechanical sweepers | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
RD1.7 | End-to-end paving of the road |  |  | 2023-03-01 |  | Yes | Length of Road (km) |  |  | 90 | 90 | 0 | 0 | As per information from ULB, pucca pavements is in 70% Roads. Through the letter dated 17/03/2021 of Uttarakhand Pollution Control Board, an amount of Rs. 110 lakhs have been approved for Paving Solder along the urban Roads for improving air pollution, on which tenders have been invited. Work has completed for 7 km stretchand further will be completed in two-three months. Ministry of Road Transport and Highways has approved to construct 4-lane road in 226.2 km to 228.2 km from Geeta Nagar Chowk to Chandrabhaga Bridge and construction of both side solders by interlocking tiles from 218.2 km to 226.2km on NH-58 in the Uttarakhand under EPC mode, on which tender has been invited and process of agreement is in process. Construction of paving road is in process. 3500 meter of raod paving has been done.
RD1.8 | Road design improvement | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
RD1.9 | Introduce water fountain at major traffic intersection | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
RD1.10 | Widening of Roads | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
RD1.11 | Improvement of infrastructure for decongestion of road. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
RD1.12 | Designing and Construction of environment friendly roads | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
RD1.13 | Implement truck loading guidelines; use of appropriate enclosures for haul trucks; gravel paving for all haul routes. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
RD1.14 | Identify road stretches with high dust generation | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
RD1.15 | Create Proper Pedestrian Infrastructure | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
RD1.16 | All the canals/nallah's side roads should be brick lined. Proper plantation also carried out. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
RD2 | Creation of green cover
RD2.2 | Creation of green buffers along the traffic corridors and their maintenance | As per information from ULB 15% green belt is there in the city. | 2021-03-01 | Nil | Nil | Nil | Number of trees | Nil | Nil | 10 | 10 | 0 | 0 | As per information from ULB 10% green belt is there in the city. Tree plantation has been done on the dividers as well by ULB
RD2.3 | Necessary changes in byelaws- Greening of open areas, gardens,commun ity places, schools and housing societies | As per information from ULBs 10% area of the city is green cover | 2023-03-01 | Nil | Nil | Nil | Number of Trees | Nil | Nil | 10 | 10 | 0 | 0 | As per information from ULB, Action of Tree plantation has been done at Nagar Nigam Park, Aastha path, Schools & Social places. On the Occassion of Environment day, UNDP and Nagar Nigam has planted medicinal plants and other plants at nigam astha and smriti van and distributed medicinal plants to all officers of Nagar Nigam, covid vaccination team at government Hospitals and people whoc came to get vaccinated and aware common man regarding Environment conservation. On occassion of Harela (16th July, 2021), 24420 trees has been planted . Tree has been planted on the dividers and regular sprinkl of water is being done at astha path and dividers. Approx. 1200 mtrs. of green plantation has been done on astha path.
RD2.4 | Urban Greening with vertical garden | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
RD2.5 | Builders should leave 25%/33% area for green belt in residential colonies to be made mandatory. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
RD2.6 | Adopt street design guidelines for paving of roads and footpaths (hard and soft paving) and vegetative barriers. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
RD2.7 | Implementation of maintaining at least 33% forest cover area in the city in master plan. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
RD3 | Installation of WAYU (Wind Augmentation and Purifying Units) at urban traffic intersection. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
C&D1 | Construction Activities
C&D1.1 | Ensure transportation of construction materials in covered vehicles | Enforcement actions are in progress with respect to non-covering of goods in goods vehicles. | Nil | In Process | Nil | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | 2019-20: 36 vehicles are challaned 2020-21: 36 2021-22: 48 (upto 30.09.2021)
C&D1.2 | Strict enforcement of CPCB guidelines for construction (use of green screens, side covering of digging sites, etc.) | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Ac tion Plan
C&D1.3 | Restriction on storage of construction materials along the road. | As per ULB information, storage of construction materials along the road is prohibited. | 2021-03-01 | In Process | Nil | Nil | Amount / Number | Nil | Nil | Nil | Nil | Nil | Nil | In its meeting dated 18.12.2019, DM Dehradun directed to PWD and NHAI to ensure immediate compliance of the same. As informed by ULB, storage of construction materials along the road is prohibited and there is provision of fine as per the Gazette notification and SWM Rules, 2016. Land has been identified at Virbhadra, Rishikesh for disposla of C& D waste. Land Transfer is in process with Revenue Department. 2019-20: 604 vehicles are challaned (Rs. 739100 amount collected) 2020-21: 46 (Rs. 24000 amount collected) (as on 30.09.2021)
C&D1.4 | Covering of construction site. | Execution of Action Plan is in progress. | 2021-03-01 | Nil | Nil | Nil | Number | Nil | Nil | Nil | Nil | Nil | Nil | Presently, There are total 11 sites which are under construction of above 10,000 sq.ft built-up area and they all are properly covered.
C&D1.5 | To create separate space/zone to handle solid waste, C&D waste and other waste in the city | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
C&D1.6 | To mandate facility of tar road inside the construction site for movement of vehicles carrying construction material | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
C&D1.7 | Promotion of the use of prefabricated blocks for building construction | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
C&D1.8 | Enforcement of Construction and Demolition Waste Rules | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
C&D1.9 | Control measures for fugitive emissions from material handling-conveying and screening operations | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
C&D1.10 | Develop and implement dust control measures for all types of construction activities -- buildings and infrastructure. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
C&D1.11 | Enforce restrictions on construction activities within urban airshed zones during high pollution period | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
C&D1.12 | Frame and implement policy for segregation of construction and demolition waste and provide a network of decentralized C&D waste segregation and collection sites across the city. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
C&D1.13 | Promote recycling of construction and demolition waste. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
*AP1.1 | Transportation of municipal solid wastes, construction materials and debris in covered system | 20 Door to Door vehicles | Nil | Nil | Nil | Nil | Number | Nil | Nil | Nil | Nil | NIl |  | Continues enforcement action is being taken in relation to the non-carrying of goods by the enforcement team, Rishikesh. A total of 36 vehicles have been invoiced (challaned) in the financial year 2019 – 2020, 36 vehicles in financial year 2020 – 2021 for not covering the good, 48 vehicles in the year 2021-2022 (upto September, 2021).
[10 empty] | 218 | 218 | 0 | 0
*AP - Additional points

## vehicles
VE1 | Improve and strengthen PUC programme | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated | Funds released | Funds Utilized | Additional Funds Required | Remarks
VEHICLES
VE1.1 | Number of PUC centers in the city | _ |  | 2023-03-01 | Nil | Nil | Number | Yes | Nil | 10 | 0 | 0 | 10 | Present numbers of PUC checking centers are increased from 17 to 24.
VE1.2 | Regular checking of Vehicular emission and issue of Pollution under Control Certificate (PUC) | Every year at least 10% of vehicles will be challaned. |  | 2023-03-01 | Nil | Nil | Number |  | 0 | 10 | 0 | 0 | 10 | 1. Present numbers of PUC checking centers are increased from 17 to 24. 2. Year wise details of PUC investigation of vehicles: 2019-20: 23046 2020-21: 27621 2021-22: 16861 (up to 30th September, 2021) July-September, 2021: 8475
VE1.3 | Auditing and reform of Pollution Under Control (PUC) certification | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE1.4 | linking of PUC centres with remote server and eliminate manual intervention in PUC testing. | In Progress |  | 2021-03-01 | Nil | Nil | Number |  | Nil | Nil | Nil |  | Nil | At present all the pollution detection centers in the state have been integrated with the single web-based software ‘Vehicle 4.0’. The total number of registered vehicles in the office are 1,42,139. According to the report of Vehicle 4.0, the details of pollution certificates issued by various pollution investigation centers operated under the area till March 2021 are given below: 2019-20: 23046 2020-21: 27621 2021-22: 16861 July-September, 2021: 8475
VE1.5 | Integrate on-board diagnostic (OBD) system fitted in new vehicles with vehicle inspection. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE1.6 | Link PUC certificates with annual vehicle insurance | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE2 | Vehicle labelling or sticker programme
VE3 | Freight transport | Overall Grade (VE3.1+VE3.2…/Total points) | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE3.1 | Use of off-peak passenger travel times to move freight and restrict the entry of heavy vehicles into cities during the day to continue | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE3.2 | Provide truck rest areas/parks along national and state highways to prevent entry of trucks into cities during peak hours. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE3.3 | Diversion of truck traffic | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE3.4 | Check overloading: Use weigh-in-motion bridges / machines (WIM) and Weigh bridges at entry points to the city to check the payload of commercial vehicles. As per the CMVR, a penalty of 10 times the applicable rate for overloaded vehicles is applicable. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE3.5 | Define routes, permits, fares, vehicle design and safety standards, and vehicle technology standards for para-transit vehicles. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE4 | Clean fuel and fuel Quality | Overall Grade (VE4.1+VE4.2…/Total points) | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE4.1 | Check on fuel adulteration and random monitoring of fuel quality data | _ | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE4.2 | Alternative clean fuel policy for vehicle | _ |  | 2023-03-01 | Nil | Nil | Number and Enforcement | Nil | Nil | Nil | Nil | Nil | Nil | 1. In Rishikesh city, currently no CNG / LPG fuel station operated. 2. Due to operation of CNG fuel stations in Dehradun and Haridwar, currently 40 CNG vehicles and 113 LPG vehicles have been registered in the office of ARTO. 3. ARTO also suggested to RTO Dehradun to replace Diesel auto rickshaw vehicles to CNG Fuel driven auto rickshaw vehicles in the future.
VE4.3 | Bio fuel policy |  | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE5 | Parking Management | Overall Grade (VE5.1+VE5.2…/Total points) | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE5.1 | Prevent parking of vehicles in the non-designated areas |  | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE5.2 | Development of Multi-layer parking |  | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE5.3 | Penalise parking of vehicles in non designated areas |  | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE6 | Strengthening of Public Transportation | Overall Grade (VE6.1+VE6.2…/Total points) | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE6.1 | Regulate the taxi industry |  | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE6.2 | Assess and introduce a city bus system of appropriate fleet size of small buses and desirable bus type replete with GPS tracking, ETVMs for fare collection and Passenger Information Systems. | _ | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE6.3 | Develop route plan for bus operation; target trunk roads | _ | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE6.4 | Intermediate public transport (IPT) and bus system | _ | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE6.5 | Introduction of new electric buses (with proper infrastructure facilities such as charging stations) and CNG buses for public transport which will reduce plying of private vehicles on road and help to curb tail-pipe emissions. | _ | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE6.6 | CNG infrastructure for auto gas supply in the city and transition of public transport vehicles to CNG mode Introduction of e-buses for Public transport in metro cities | _ | Nil | 2023-03-01 | Nil | Nil | Number and Enforcement | Nil | Nil | Nil | Nil | Nil | Nil | 1. In Rishikesh city, currently no CNG / LPG fuel station operated. 2. Due to operation of CNG fuel stations in Dehradun and Haridwar, currently 40 CNG vehicles and 113 LPG vehicles have been registered in the office of ARTO. 3. ARTO also suggested to RTO Dehradun to replace Diesel auto rickshaw vehicles to CNG Fuel driven auto rickshaw vehicles in the future.
VE6.7 | Steps for promoting battery operated vehicles like Erickshaw / E-Cart | 350 E-Ricksaws & 54 E-kart vehicles | Nil | 2023-03-01 | Nil | Nil | Number and Enforcement | Nil | Nil | Nil | Nil | Nil | Nil | As on 30.09.2021, 136 E-Ricksaws & 21 E-kart vehicles were registered. As informed from ARTO Rishikesh that 1. The operation of E-Rickshaw has not been successfully done in the routes having high inclination in Rishikesh. 2. ARTO is having proposal to ply e-rickshaws on such route in the Rishikesh city which have high load of vehicles. 3. RTO Dehradun has been suggested to replace permit for diesel auto rickshaw vehicles by CNG / LPG fuel driven auto rickshaw vehicles through permit replacement action in future.
VE6.8 |  | _ | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE6.9 |  | _ | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE7. | Traffic Congestion | Overall Grade VE7.1+VE7.2../total | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE7.1 | Conducting audit of traffic intersections and install functional traffic signals at all major intersections | _ | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE7.2 | Synchronize traffic movements/Introduce intelligent traffic system for lane-driving | _ | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE7.3 | Prepare plan for construction of diversion ways/ bypasses to avoid congestion due to nondestined vehicles. | _ | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE7.4 | Prepare plan for widening of road and improvement of infrastructure for decongestion of road. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE8 | Launch Public awareness campaign for air pollution control, vehicle maintenance, minimizing use of personal vehicle, lane discipline, etc. | In Progress | Nil | Nil | Nil | Nil | Enforcement | [6 empty] | 01 Workshops was conducted at DIT University to discuss various issues related to air pollution and its mitigations measures. Board has also distributed pamphlets and posters on Do’s and Don’ts for Air Pollution Control. Also, advertisement for the awareness has been published in Daily News Papers by UKPCB. A press release has been published in Daily News Papers by RTO Rishikesh. Under the road safety program, the general public is made aware of their vehicles from time to time for maintenance, fitness certificate PUC and minimum use of private vehicles.
VE9 | Periodic calibration test of vehicular emission monitoring instrument. | Implemented | Nil | Nil | Nil | Nil | Enforcement | Nil | Nil | 10 | 0 | 0 | 10 | Presently, the periodic calibration facility is arranged in departmental software. Under which it has been made mandatory by the operator to update the calibration for regular operation of the pollution detection centre. Presently, all the pollution testing centers are updating their periodic calibration certificate on the departmental software / portal. If the periodic calibration of attest centre ends, then the operation of the test centre stops automatically.
VE10 | To check the calibration of emission monitoring equipments, housed in Emission Testing Centers (ETCs) once in 6 months to know the status of equipments | _ | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE11 | Phase out old vehicles and vehicle scrappage policy | Overall Grade (VE11.1+VE11.2…/Total points) | [11 empty] | Not Incorporating in Action Plan
VE11.1 | Inspection /maintenance to all BSII & BS III
VE11.2 | Restriction on plying and phasing out of 15 years old commercial diesel driven vehicles. | In Progress |  |  |  |  | Number | [6 empty] | 1. According to office record of ARTO Rishikesh, number of commercially driven Diesel Vehicles older than 15 years are 1635 (as on 30.09.2021). 2. Registration of such 1635 vehicles has not been renewed after completing the age of 15 years. 3. Regarding the ban on 15 years old commercial vehicles, the letter has been sent to Additional Transport Commissioner by RTO Dated 29.02.2020. 4. Registration of 7343 private vehicles has not been renewed after completing the age of 15 years
VE11.3 | Enforcement of law against visibly polluting vehicles: remove them from road, impose penalty, and launch extensive awareness drive against polluting vehicles. | In Progress |  |  |  |  | Number |  |  | Nil | Nil | Nil |  | Currently, vehicles are being fitted through the “M-Fitness: application, in which the photographs of vehicles are also uploaded and according to the standards the proof of fitness certificate is being issued to the vehicles. Details of proceedings against vehicles without fitness proof: 2018-19: 684 2019-20: 737 2020-21 : 275 2021-22 : 188 (as on 30.09.2021) July-September, 2021: 81 Year wise details of fitness certificate: 2018-19: 8473 2019-20: 6644 2020-21 : 5081 2021-22 : 2476 July-September, 2021: 2121
VE11.4 | Initiate steps for retrofitting of particulate filters in diesel vehicles, when BS-VI fuels are available. | _ | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE11.5 | To increase fine on vehicle owners (not drivers) where the visible smoke is emitted and noticed. | _ | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE11.6 | Examine existing framework for removing broken down buses or trucks from roads and create a system forspeedy removal and ensuring minimal disruption to traffic from such buses or trucks. | _ | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE11.7 | The restriction on use of two stroke vehicles in phased manner (2-Stroke, 3-stroke) | _ | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE12 | NMT
VE12.1 | Introducing cycle tracks along with the roads | _ | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE12.2 | Prepare and implement zonal plans to develop an NMT network | _ | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not Incorporating in Action Plan
VE13 | Compact city development to reduce distances and improve access | [12 empty] | Not Incorporating in Action Plan
AP1 | Increase in Penalty of Rs 1000 to Rs 5000 in case of violation of PUC. (for both cities) | Implemented |  |  |  |  | Number | [6 empty] | According to the provisions contained in sub section 190 (2) of section 200 of the Motor Vehicles Act 1988 by notification of Uttarakhand Govt. Section-1 dated 24.09.2019 in the prosecution for not having Pollution Control Certificate , Rs 2500 will be charged for the first time and Rs 5000 for the second or subsequent offense In case on not having PUC certificate, following penalties have been received so far by transport department, Rishikesh: 2019-20: 9.45 Lakh 2020-21 : 8.34 Lakh 2021-22 : 1.59 Lakh (as on 30.09.2021) July-September, 2021: 0.44 lakh
[10 empty] | 30 | 0 | 0 | 30

## Industries
INDUSTRIES
IP1 | Industrial air pollution control | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated | Funds released | Funds Utilized | Additional Funds Required | Remarks
IP4.5 | Restriction on using un-authorised fuels in industries | Nil | Nil | 2023-03-01 | Nil | Nil | Yes |  | Nil | Nil | Nil | NA | NA | Approved fuel where Biomass, wood & coke are allowed. Pet coke and Furnace Oil for the new units are restricted. Roots and chipped material from plyboard industries are allowed.
*AP1.2 | Installation and operation of advance air pollution control systems and Continuous Ambient Air Quality Monitoring System in Industries located in and around Kashipur and at M/s Hindustan National Glass Industries Ltd, Rishikesh | In Progress |  | 2023-03-01 |  |  | Enforcement |  | Nil | Nil | Nil | NA | NA | Around 30KLD RFO is being used as fuel by M/s Hindustan National Glass Industries Ltd. Veerbhadra Rishikesh. Currently 90m height chimney is operated with a natural draft as an Air Pollution Control System in Industry. Regional Officer directed to implement the installation of CAAQMS from the unit.
*AP1.4 | Compliance of guidelines on D.G. sets regarding use of retrofitted emission control system (PM captured efficiency 70%) capacity equal to or above 800 KW | In Progress |  | 2021-03-01 |  |  | Number |  | Nil | Nil | Nil | NA | NA | Survey by Regional officer, PCB is in process,
*AP1.5 | Removal of Open DG sets | In Progress |  | 2023-03-01 |  |  | Number |  | Nil | Nil | Nil | NA | NA | As per report of Regional Officer and Municipal Corporation a total of 29 Open DG sets are reported in Rishikesh. Sub Divisional Magistrate on dated 12.03.2021 is directed to immediate seal the open D.G. Sets. During inspection on 26.06.2021 by RO, Dehradun and Nagar Nigam, Rishikesh, 27 open D.G. set has found for which Sub Divisional Magistrate on dated 08.07.2021 is directed to immediate seal the open D.G. Sets.

## Waste &Biomass
BB1 | Biomass Burning | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated | Funds released | Funds Utilized | Additional Funds Required | Remarks
WASTE AND BIOMASS- DUMPING AND BURNING
BB1.1 | Regular check and control of burning of municipal solid wastes | In progress |  | 15.10.19 | Continous |  | Amount |  |  |  | Nil | Nil | Nil | Strict instructions have been issued to field employees by Nagar Nigam Rishikesh and concerned Regional supervisor is closely monitored their respective areas. • Anti littering Act (From Jan 2021 to 30 June 2021) No of Challan 102 Amount Collected – Rs 38200 • Plastic waste Management Challan (From Jan 2021 to 30 June 2021) No of Challan 39 Amount Collected – Rs 70500 Burning of plastic and solid waste has been prohibited in the area under Nagar Nigam. Regular inspection is being carried out regarding the same.
BB1.2 | Defaulters for open burning to be imposed fines | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
BB1.3 | Identify Garbage burning locations and | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
BB1.4 | Prohibition/complete ban on garbage burning. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
BB1.5 | Launch extensive drive against open burning of bio-mass, crop residue, garbage, leaves, etc. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
BB1.6 | Construction of advanced waste management Site. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
BB1.7 | Regular collection and control of municipal solid wastes. | In Progress |  | 2021-03-01 |  |  | Amount /Number |  |  |  | Nil | Nil | NA | 1. A total of 80 MTD Waste is collected from Door-to-Door Collection. 2. LB has achieved almost 100% Door to Door Collection of Waste. It is done by 18 workers/ helpers with 30 Door-to-Door vehicles. 3. Frequency of lifting of wastage - 3 rounds per vehicle (Morning 6:00AM to Afternoon 02:00PM). 4. A Nala Gang has been formed by Nagar Nigam Rishikesh for desilting the waste from drains.
BB1.8 | Providing Organic Waste Compost machines , decentralization of processing of Waste, dry waste collection centers. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
BB1.9 | Awareness for controlling of burning of agricultural waste and crop residues. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
BB1.10 | No plot should be left open more than 02 years and planting of trees must be mandatory on vacant plots. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
BB1.11 | Dead Bodies of Animals should be disposed through proper treatment facility like rendering plant etc | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
BB2 | Ensure segregation of waste at source | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
BB3 | Proper collection of Horticulture waste and its disposal following composting-cumgardening approach | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
BB4 | Recycling plants for dry waste. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
BB5 | Ambient air quality monitoring of municipal dumping sites and parks | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
BB6 | Check/stop on Stubble Burning | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
BB7 | Action plan to minimize the forest fire | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
BB8 | Use of Piped Natural Gas (PNG) for Human cremation. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
BB9 | Use of satellite based monitoring as well as mobile spot check squads for enforcement | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
BB10 | Landfill fire
BB10.1 | Proper management of landfill sites to prevent spontaneous fire | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
BB10.2 | Adopt roadmap for zero landfill policy to promote decentralized waste segregation, reuse and recycling | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
BB11 | Fire crackers—regulate to control their usage | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
DF1 | Domestic Fuel
DF1.1 | Increasing the LPG connections in low income strata. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
DF1.2 | Ensuring promotion and use of cleaner fuel (i.e. LPG) instead of coal fired chulas or fire-woods in the hotels and open spaces | In Progress |  | 2023-03-01 |  |  | Number |  |  |  | Nil | Nil | Nil | By the cleaning inspector of Nagar Nigam Rishikesh, survey of all the Dhabas / Hotels / Eateries is going on to ensure the usage of cleaner fuel for their commercial purposes. 21264 no. of Houses, which comes comes under Nagar Nigam, Rishikesh has LPG connection.
DF1.3 | Introduce schemes for providing subsidized LPG connections as well as providing means of finance to small tea vendors/hawkers using kerosene stoves in order to reduce emissions from burning of kerosene | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
DF1.4 | To mandate LPG/Bio gas in commercial eateries. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
DF1.5 | Ensuring 100% electrification and uninterrupted electric supply with in the city. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
DF1.6 | Ensure easy availability of affordable cleaner cooking fuels (LPG in urban areas & biogas in rural areas) | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
DF1.7 | Introduction of improved chullahs (low emission chullahs) | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
DF1.8 | Implemen tation of Pradhan Mantri Ujjwala Yojana (PMUY) | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
DF1.9 | Shift to LPG from solid fuel & kerosene for domestic applications | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
DF1.10 | Use of LPG in Bakeries | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
DF1.11 | Adopting Better construction practices with PM reduction of 50% | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan

## Air Quality Data
AIR QUALITY DATA
|  | Nagar Palika Parishad (2021) | [8 empty] | SPS Hospital (2021)
Action Code | Action Point | January | February | March | April | May | June | July | August | September | January | February | March | April | May | June | July | August | September
AQ1.1 | Monthly averages for PM2.5 (In µg/m3) | 79.36 | 92.54 | 92.54 | 88.22 | 53.14 | 66.63 | 71.36 | 76.43 | 60.72 | NA | NA | NA | NA | NA | 76.68 | 76.68 | 74.92 | 63
AQ1.2 | Monthly averages for PM10 (In µg/m3) | 151.15 | 161.33 | 176.36 | 176.74 | 75.9 | 95.63 | 116.89 | 119.39 | 110.73 | 146.78 | 172.79 | NA | 188.65 | 84.1 | 121.52 | 121.52 | 123.27 | 113.62
AQ1.3 | Monthly averages for SO2 (In µg/m3) | 22.11 | 22.34 | 21.27 | 18.41 | 16.68 | 19.51 | 19.1 | 19.54 | 17.41 | 21.78 | 23.35 | 22.99 | 20.2 | 17.51 | 19.22 | 19.22 | 19.72 | 17.72
AQ1.4 | Monthly averages for NO2 (In µg/m3) | 27.17 | 26.65 | 26.49 | 25.09 | 22.22 | 24.45 | 23.82 | 24.11 | 23.99 | 26.71 | 27.38 | 27.38 | 26.33 | 21.68 | 24.35 | 24.35 | 25.35 | 24.09
AQ1.5 | Annual averages for PM2.5 (In µg/m3) | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
AQ1.6 | Annual averages for PM10 (In µg/m3) (Jan-Dec 2020) | 108.18
AQ1.7 | Annual averages for SO2 (In µg/m3) (Jan-Dec 2020) | 18.66
AQ1.8 | Annual averages for NO2 (In µg/m3) (Jan-Dec 2020) | 23.24
AQ1.9 | Monthly Meterological Data | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA