## Summary
Basic Information
Name of Non Attainment City |  | Kashipur
Sate/ Union Territory |  | Uttarakhand
Name of Nodal Officer at PCB/ PCC |  | Dr. Ankur Kansal
Email Id |  | ncaputtarakhnd@gmail.com
Contact Number |  | 9412992375
Date till which progress is submitted |  | 31.03.2021
Action Point Code | Sector | Total Number of Actions | Number of Actions Completed | Number of Actions Under Progress | Required funds (in Lac)
CB | CAPACITY BUILDING, MONITORING NETWORK AND SOURCE APPORTIONMENT including Salary of 01 JRF | 5 | 3 | 2 | 375
PO | PUBLIC OUTREACH | 5 | 4 | 1 | 50
RD/ C&D | ROAD DUST AND CONTRUCTION & DEMOLITION | 9 | 8 | 1 | 1395
VE | VEHICLES | 11 | 10 | 1 | 30
IP | INDUSTRIES | 6 | 5 | 1 | _
BB/DF | WASTE AND BIOMASS- DUMPING AND BURNING | 5 | 3 | 2 | 40
AQ | AIR QUALITY DATA | 6 | 6 | 0 | _
|  |  |  | Total | 1890

## Capacity Building & SA
CAPACITY BUILDING, MONITORING NETWORK AND SOURCE APPORTIONMENT (Kashipur)
Action Point Code | Action Point | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated | Funds released | Funds Utilized | Additional Funds Required | Remarks
CB1.1 | CAAQMS | 0 | 1 | 2021-03-01 | No | Nil | Yes | Nil | Nil | 230 | Nil | NA | 230 | It is agreed by the GPIs of Kashipur that the CAAQMS will be established by them by making a consortium. UKPCB has published Tender for procurement of 01 CAAQMS for Kashipur.
CB1.2 | Manual Stations | 1 | 3 | 2021-03-01 | No | Nil | Yes | Nil | Nil | 25 | 6 | 5.8 | 19 | Already 01 Monitoring station is in operation at Kashipur. Equipment for operating 02 more manual stations have been procured and the stations will be started in next quarter (Apr-jun-2021)
CB2 | Air Quality Forecasting | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
CB3 | Assessment of sources
CB3.1 | Emission Inventory | Completed |  | 2023-03-01 |  |  | Yes | Nil | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
CB3.2 | Emission tracking system | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | 40 | Nil | NA | 40 | Awarded to TERI, New Delhi. Winter monitoring has been carried out.
CB3.3 | Source Apportionment Study | Completed |  | 2023-03-01 |  |  | Yes | Nil | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
CB3.4 | Health Impact Studies | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | 40 | Nil | NA | 40 | Awarded to TERI, New Delhi. Winter monitoring has been carried out.
CB3.5 | Exposure Impact Studies | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | NA | Not incorporated in Action Plan
CB4 | Training & Capacity Building
CB4.1 | Training & skill development of public officals | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | 5 | 0.5 | 0.41 | 4.5 | Organized workshop for city specific stakeholders in September 2019.
CB4.2 | Infrastructure development (Laboratory/ AQM Cell | In progress | Nil | Nil | Nil | Nil | Nil | Nil | Nil | 25 | 13.5 | 5.45 | 11.5 | Letter has been issued to create AQM Cell in kashipur.
CB4.3 | Enforcement Units | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Not incorporated in Action Plan
CB5 | Emergency Response System | In progress |  | 2021-03-01 | Nil | Nil | Yes | Nil | Bieng Finalised | 10 | Nil | Nil | 10 | Bieng Finalised
[10 empty] | 375 | 20 | 11.66 | 355

## Public Outreach
PUBLIC OUTREACH
Action Point Code | Action Point | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated | Funds released | Funds Utilized | Additional Funds Required | Remarks
PO1 | Public Outreach
PO1.1 | Daily Air Quality Public Information Dissemination System | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in Action Plan
PO1.2 | Social Media Platforms | Disigned the posters & posted on various social media platforms. | Nil | Nil | Nil | Nil | Yes |  | Details of social media platforms | Nil | Nil | Nil | Not required | Twitter @Uttarakhanpcb
PO1.3 | Issue public advisory for prevention and control of air polltuion | Publish the Advertisement |  | 15.10.2019 | Nil | Nil | Yes |  | Number and detail of public advisories per quarter | 30 | 30 | 0 | 0 | 01 Workshops was conducted at DIT University to discuss various issues related to air pollution and its mitigations measures. Board has also distributed pamphlets and posters on Do’s and Don’ts for Air Pollution Control. Also, advertisement for the awareness has been published in Daily News Papers. Poster, banner and awareness campaign is being done by Nagar Nigam Kashipur. A press release has been published in Daily Newspapers. by RTO Kashipur. RTO has also sent letter to the Gram Pradhan of all the Gram Panchayat of Kashipur, Jaspur, Bajpur Tehsil to conduct online pollution checking of vehicles under their respective village area. Pamphlets are also distributed by the RTO at Schools, Colleges, Union & pollution checking centers. Under the road safety program, the general public is made aware of their vehicles from time to time for maintenance, fitness certificate PUC and minimum use of private vehicles.
PO1.4 | Deeper public engagement and consultation (workshops/ programmes in schools/ colleges) |  |  | 2021-03-01 | Nil | Nil | Yes |  | Number & details of public awareness events held per quarter | 20 | 20 | 0 | 0 | Due to pandemic academic session 2020-21 is not operated physically. In future as and when schools open physically, this will be carried out. Chief Education Office, Udham Singh Nagar has directed Block Education Officer, Kashipur to take necessary steps for creating awareness amongst the students related to air pollution control. .
PO1.5 | Launch mobile app to update public about status of air quality | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in Action Plan
PO2 | Public Greivance Redressal System | Implemented | 2021-03-01 | Completed | Nil | Nil | Yes |  | Nil | Nil | Nil | Nil | Nil | Web based Android app for redressal of public complaints on air pollution along with a supervisory control for the disposal of complaints has been created by UKPCB.
PO2.1 | App Based System |  | 2021-03-01 | Completed | Nil | Nil | Yes |  | Resolving process is in progress | Nil | Nil | Nil | Nil | NCAP App for Air related issues.
PO2.2 | Helpline Number | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in Action Plan
[10 empty] | 50 | 50 | 0 | 0

## Road dust & C&D
ROAD DUST AND CONTRUCTION & DEMOLITION
RD1 | Road dust | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated | Funds released | Funds Utilized | Additional Funds Required | Remarks
RD1.1 | Immediate lifting of solid waste generated from disilting and cleaning of municipal drains for its disposal | In progress |  | 2021-03-01 |  |  | Yes |  |  | 198 | 99 | 0 | 99 | 1. A total of 54 MTD Waste is generated. 2. ULB has achieved almost 100% Door to Door Collection of Waste. It is done by 2 teams of 20 workers in each. 3. Lifting of garbage and desilting waste from drains is done on daily basis according to roaster.
RD1.2 | Maintain potholes free roads | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
RD1.3 | Regular cleaning of street surfaces and spraying of water to suppress dust. | Manual Sweeping: - 100%, 05 tanker of Water Sprinklers |  | 2021-03-01 |  |  | Yes |  |  | 9 | 9 | 0 | 0 | As informed by ULB, there are 05 water sprinkling tankers used for spraying water on streets. UKPCB has disbursed funds (as received from GOI under NCAP) for procurement of Water Tankers.
RD1.4 | Black-topping of unpaved road | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Not incorporated in the Action Plan
RD1.5 | Minimize earth cutting from the hills to prevent dust generation. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
RD1.6 | To take appropriate action to remove road dust/silt regularly by using mechanical sweepers | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil
RD1.7 | End-to-end paving of the road | In progress |  | 2023-03-01 |  |  | Yes |  |  | 1000 | 100 | Nil | 900 | As informed by ULB, wherever, Construction of pucca pavement along the road can take place is almost done. UKPCB has disbursed funds (as received from GOI under NCAP) for construction of Pucca Pavement.
RD1.8 | Road design improvement | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
RD1.9 | Introduce water fountain at major traffic intersection | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
RD1.10 | Widening of Roads | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
RD1.11 | Improvement of infrastructure for decongestion of road. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
RD1.12 | Designing and Construction of environment friendly roads | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
RD1.13 | Implement truck loading guidelines; use of appropriate enclosures for haul trucks; gravel paving for all haul routes. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
RD1.14 | Identify road stretches with high dust generation | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
RD1.15 | Create Proper Pedestrian Infrastructure | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
RD1.16 | All the canals/nullah's side roads should be brick lined. Proper plantation also carried out.
RD2 | Creation of green cover | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
RD2.2 | Creation of green buffers along the traffic corridors and their maintenance | In progress |  | 2021-03-01 |  |  | Yes |  |  | 94 | 21 | Nil | 73 | Tree plantation along the road wherever possible is in place. Forest Department has not submitted its report.
RD2.3 | Necessary changes in byelaws- Greening of open areas, gardens,commun ity places, schools and housing societies | As per information from ULBs 10% area of the city is green cover |  | 2023-03-01 |  |  | Yes |  |  | 94 | 21 | Nil | 73 | 1. 10 % of the city area is having green cover. 2. Appx. 60% of the area around 50 km of the City is covered by Tree / forest. 3. Plantation is being done to develop the reserved garden. 4. All schools and housing societies and others have been directed to develop the green belt in their premises by ULB.
RD2.4 | Urban Greening with vertical garden | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
RD2.5 | Builders should leave 25%/33% area for green belt in residential colonies to be made mandatory. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
RD2.6 | Adopt street design guidelines for paving of roads and footpaths (hard and soft paving) and vegetative barriers. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
RD2.7 | Implementation of maintaining at least 33% forest cover area in the city in master plan. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
RD3 | installation of WAYU (Wind Augmentation and Purifying Units) at urban traffic intersection. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
C&D1 | Construction Activities
C&D1.1 | Ensure transportation of construction materials in covered vehicles | Implemented |  | 2021-03-01 |  |  | Yes | [6 empty] | Continuous enforcement actions are being taken with respect to non-covering of goods in cargo vehicles. For the financial year 2020 – 21, by the prosecution team a total of 68 vehicles has been invoiced (challaned) for not covering the goods.
C&D1.2 | Strict enforcement of CPCB guidelines for construction (use of green screens, side covering of digging sites, etc.) | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
C&D1.3 | Restriction on storage of construction materials along the road. | Implemented |  | 2021-03-01 |  |  | Yes | [6 empty] | As informed by ULB, storage of construction materials along the road is prohibited and there is provision of fine as per the Gazette notification and SWM Rules, 2016. 2020-2021: 2 challans (Rs 600 amount collected)
C&D1.4 | Covering of construction site. | In the first phase will be implemented at sites having more than 10,000 sq. Mt. Covered area |  |  |  |  | Yes | [6 empty] | There is no construction site (having covered area >10,000 SQMT) as enquired except construction of flyover (as on 31.03.2021).
C&D1.5 | To create separate space/zone to handle solid waste, C&D waste and other waste in the city | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
C&D1.6 | To mandate facility of tar road inside the construction site for movement of vehicles carrying construction material | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
C&D1.7 | Promotion of the use of prefabricated blocks for building construction | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
C&D1.8 | Enforcement of Construction and Demolition Waste Rules | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
C&D1.9 | Control measures for fugitive emissions from material handling-conveying and screening operations | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
C&D1.10 | Develop and implement dust control measures for all types of construction activities -- buildings and infrastructure. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
C&D1.11 | Enforce restrictions on construction activities within urban airshed zones during high pollution period | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
C&D1.12 | Frame and implement policy for segregation of construction and demolition waste and provide a network of decentralized C&D waste segregation and collection sites across the city. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
C&D1.13 | Promote recycling of construction and demolition waste. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA | Nil | Not incorporated in the Action Plan
AP1.1 | Transportation of municipal solid wastes, construction materials and debris in covered system (for both cities) | Implemented |  |  |  |  | Yes |  |  | Nil | Nil | Nil | Nil | All vehicles for transportation of municipal solid wastes, construction materials and debris are covered. Construction & Demolition waste is further used to filling up voids and ground around the city premises
[10 empty] | 1395 | 250 | 0 | 1145
*AP - Additional Points

## Vehicles
VEHICLES
VE1 | Improve and strengthen PUC programme | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated | Funds released | Funds Utilized | Additional Funds Required | Remarks
VE1.1 | Number of PUC centers in the city | 18 |  | 2023-03-01 |  |  | 18 | Nil | Nil | 10 | 0 |  | 10 | Present numbers of PUC checking centers are increased from 16 to 18.
VE1.2 | Regular checking of Vehicular emission and issue of Pollution under Control Certificate (PUC) | In progress |  | 2023-03-01 |  |  | Yes | Nil | Nil | 10 | 0 | 0 | 10 | 1. Present numbers of PUC checking centers are increased from 16 to 18. 2. Continuous checking is done by the Enforcement unit Kashipur. Action against the vehicles not having PUCs during the checking: 2018-19: 1030 2019-20: 1447 2020 - 21: 501 3. Year wise details of PUC investigation of vehicles: 2019-20: 47692 2020-21: 53366
VE1.3 | Auditing and reform of Pollution Under Control (PUC) certification | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE1.4 | Linking of PUC centres with remote server and eliminate manual intervention in PUC testing. | Total 100853 pollution certificates has been issued by various pollution checking centers as on 31.03.2021 |  | 2021-03-01 |  |  | Yes | Nil | Nil | Nil | Nil | NA |  | All the pollution detection centers operated under kashipur jurisdiction are integrated with the vehicle 4.0 portal. Details of pollution certificates of vehicles are also being displayed in the M-transport application. Total number of PUC Certificates issued by PUC center from July 2019 to 31.03.2021 are 100853.
VE1.5 | Integrate on-board diagnostic (OBD) system fitted in new vehicles with vehicle inspection. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE1.6 | Link PUC certificates with annual vehicle insurance | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE2 | Vehicle labelling or sticker programme | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE3 | Freight transport | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE3.1 | Use of off-peak passenger travel times to move freight and restrict the entry of heavy vehicles into cities during the day to continue | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE3.2 | Provide truck rest areas/parks along national and state highways to prevent entry of trucks into cities during peak hours. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE3.3 | Diversion of truck traffic | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE3.4 | Check overloading: Use weigh-in-motion bridges / machines (WIM) and Weigh bridges at entry points to the city to check the payload of commercial vehicles. As per the CMVR, a penalty of 10 times the applicable rate for overloaded vehicles is applicable. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE3.5 | Define routes, permits, fares, vehicle design and safety standards, and vehicle technology standards for para-transit vehicles. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE4 | Clean fuel and fuel Quality | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE4.1 | Check on fuel adulteration and random monitoring of fuel quality data | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE4.2 | Alternative clean fuel policy for vehicle | In progress |  | 2023-03-01 |  |  | Yes | [6 empty] | 1. There is 01 CNG Supply station in operated in Kashipur. 2. As on 31.03.2021, a total of 232 CNG / LPG driven commercial vehicles and 1347 non-commercial vehicles are registered in Kashipur
VE4.3 | Bio fuel policy | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE5 | Parking Management | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE5.1 | Prevent parking of vehicles in the non-designated areas | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE5.2 | Development of Multi-layer parking | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE5.3 | Penalise parking of vehicles in non designated areas | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE6 | Strengthening of Public Transportation | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE6.1 | Regulate the taxi industry | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE6.2 | Assess and introduce a city bus system of appropriate fleet size of small buses and desirable bus type replete with GPS tracking, ETVMs for fare collection and Passenger Information Systems. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE6.3 | Develop route plan for bus operation; target trunk roads | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE6.4 | Intermediate public transport (IPT) and bus system | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE6.5 | Introduction of new electric buses (with proper infrastructure facilities such as charging stations) and CNG buses for public transport which will reduce plying of private vehicles on road and help to curb tail-pipe emissions. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE6.6 | CNG infrastructure for auto gas supply in the city and transition of public transport vehicles to CNG mode Introduction of e-buses for Public transport in metro cities | In progress | Nil | Nil | Nil | Nil | Yes | Nil | Nil | Nil | Nil | NA |  | 1. There is 01 CNG Supply station in operated in Kashipur. 2. As on 31.03.2021, a total of 232 CNG / LPG driven commercial vehicles and 1347 non-commercial vehicles are registered in Kashipur
VE6.7 | Steps for promoting battery operated vehicles like Erickshaw/ECart |  |  | 2021-03-01 |  |  | Yes |  |  | Nil | Nil | Nil |  | 1. No. of E-Rikshaws (P) are 3029. 2. No. of E-Rickshaws (G) are 56.
VE6.8 |  | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE6.9 |  | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE7. | Traffic Congestion | Overall Grade VE7.1+VE7.2../total | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE7.1 | Conducting audit of traffic intersections and install functional traffic signals at all major intersections | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE7.2 | Synchronize traffic movements/Introduce intelligent traffic system for lane-driving | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE7.3 | Prepare plan for construction of diversion ways/ bypasses to avoid congestion due to nondestined vehicles. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE7.4 | Prepare plan for widening of road and improvement of infrastructure for decongestion of road. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE8 | Launch Public awareness campaign for air pollution control, vehicle maintenance, minimizing use of personal vehicle, lane discipline, etc. | Publish advertisement on newspapeer |  |  |  |  | Yes | [6 empty] | 01 Workshops was conducted at DIT University to discuss various issues related to air pollution and its mitigations measures. Board has also distributed pamphlets and posters on Do’s and Don’ts for Air Pollution Control. Also, advertisement for the awareness has been published in Daily News Papers. Poster, banner and awareness campaign is being done by Nagar Nigam Kashipur. A press release has been published in Daily Newspapers. by RTO Kashipur. RTO has also sent letter to the Gram Pradhan of all the Gram Panchayat of Kashipur, Jaspur, Bajpur Tehsil to conduct online pollution checking of vehicles under their respective village area. Pamphlets are also distributed by the RTO at Schools, Colleges, Union & pollution checking centers. Under the road safety program, the general public is made aware of their vehicles from time to time for maintenance, fitness certificate PUC and minimum use of private vehicles.
VE9 | Periodic calibration test of vehicular emission monitoring instrument. | In progress |  | 2021-03-01 |  |  | Yes |  |  | 10 | 0 | 0 | 10 | RTO has issued direction to Divisional Inspector (Technical) to submit the report of Periodic Calibration of Pollution checking Machines installed in all the Pollution Checking Centers in Kashipur. Compliance is under process.
VE10 | To check the calibration of emission monitoring equipments, housed in Emission Testing Centers (ETCs) once in 6 months to know the status of equipments | [12 empty] | Not incorporated in the Action Plan
VE11 | Phase out old vehicles and vehicle scrappage policy | Overall Grade (VE11.1+VE11.2…/Total points) | [11 empty] | Not incorporated in the Action Plan
VE11.1 | Inspection /maintenance to all BSII & BS III | [12 empty] | Not incorporated in the Action Plan
VE11.2 | Restriction on plying and phasing out of 15 years old commercial diesel driven vehicles. |  |  | __ | [9 empty] | 1. According to office record of ARTO Kashipur, number of commercially driven Diesel Vehicles older than 15 years are 809 (as on 31.03.2021). 2. Regarding the ban on 15 years old commercial vehicles, the letter has been sent to Additional Transport Commissioner by RTO Dated 29.02.2020.
VE11.3 | Enforcement of law against visibly polluting vehicles: remove them from road, impose penalty, and launch extensive awareness drive against polluting vehicles. | Implemented |  | __ |  |  | Yes | [6 empty] | During the fitness of vehicles, the vehicles are properly checked by the department of inspection (technical) and a valid pollution free certificate is mandatory for the fitness of vehicles. In the prosecution of non-fitness certificate of commercial vehicles during the enforcement proceedings, details of challans issued are given below: 2018-19: 839 2019-20: 929 2020-21 : 328 (as on 31.03.21) Year wise details of fitness certificate: 2019-20: 3566 2020-21 : 2584 (as on 31.03.21)
VE11.4 | Initiate steps for retrofitting of particulate filters in diesel vehicles, when BS-VI fuels are available. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE11.5 | To increase fine on vehicle owners (not drivers) where the visible smoke is emitted and noticed. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE11.6 | Examine existing framework for removing broken down buses or trucks from roads and create a system forspeedy removal and ensuring minimal disruption to traffic from such buses or trucks. | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE11.7 | The restriction on use of two stroke vehicles in phased manner (2-Stroke, 3-stroke) | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE12 | NMT | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA
VE12.1 | Introducing cycle tracks along with the roads | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE12.2 | Prepare and implement zonal plans to develop an NMT network | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
VE13 | Compact city development to reduce distances and improve access | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | NA |  | Not incorporated in the Action Plan
AP1 | Increase in Penalty of Rs 1000 to Rs 5000 in case of violation of PUC. (for both cities) | Total collected amount against the vehicles not having PUCs during the checking:- 2019-20: Rs. 62200 2020-21 : Rs. 162500 (as on 31.03.21) |  | _ |  |  | Yes | [6 empty] | 1. It is increased from Rs 2500 to Rs 5000. 2. In case on not having PUC certificate, following penalties have been received so far by transport department, Kashipur: 2019-20: 62200 2020-21 : 162500 (as on 31.03.21) 3. According to the provisions contained in sub section 190 (2) of section 200 of the Motor Vehicles Act 1988 by notification of Uttarakhand Govt. Section-1 dated 24.09.2019 in the prosecution for not having Pollution Control Certificate, Rs 2500 will be charged for the first time and Rs 5000 for the second or subsequent offense by the Enforcement team Kashipur.
[10 empty] | 30 | 0 | 0 | 30

## Industries
IP1 | Industrial air pollution control | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated | Funds released | Funds Utilized | Additional Funds Required | Remarks
IP1.1 | To intensify monitoring of industries to reduce of emission by the industries. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.2 | Action against non-complying industrial units | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.3 | Shifting of Polluting Industries | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.4 | Ban on Polluting Industries | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.5 | Random auditing for Air pollution measures and Online reporting systems in the industries | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.6 | Conversion to side-hood suction in furnaces | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.7 | Identification of air polluting industries and their regular monitoring including use of designated fuel | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.8 | Promoting cleaner production in industries. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.9 | Fugitive emission control | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.10 | Ensuring installation/Up-gradation and operation of air pollution control devices in industries | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.11 | Action/closure against defaulting/unauthorized industrial units. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.12 | Ensuring emission standards in industries | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.13 | Disposal of all non-hazardous wastes into the designated dumping sites | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.14 | Location specific Emission reduction. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.15 | Industries allowed with stringent Environmental norms only. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.16 | Industry shall prepare plant wise inventory of vents and ensure that it is routed to vapour recovery system followed by flare system, wherever applicable. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.17 | Suitable size Condenser, receiver may be provided for recoveries of high volatiles, wherever required. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.18 | Industry should adopt “Recognized and Generally Accepted Good Engineering Practices" (RAGAGEP) | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.19 | Industry should share Hydrocarbon loss data within a month time audit completion along-with past trend data with clearly highlighting the increase or decrease in the Hydrocarbon emissions. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.20 | Regeneration frequency of Adsorption / absorption system / Activated carbon bed should be clearly defined as per the trend data of previous cycles and should be documented. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.21 | Appropriate inline sensor may be explored to gauge the efficiency of treatment system. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.22 | In line monitoring may be explored to indicate the breakeven point of Activated carbon bed (Vapour recovery system), this will minimize the losses. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.23 | Industry should include a special training module regarding “fugitive emissions and its health impacts on individual and surrounding communities” for its staff, operating personnel & Drivers to spread awareness about risk/hazard associated with spills and leaks of various chemicals. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.24 | Industry may devise an internal system to increase the vigilance on tankers stationed / parked near the factory premise to ensure that even empty tankers closed properly. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.25 | Initiated Star Rating Programme | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.26 | Bank guarantee should be taken for the compliance of conditions imposed in CTO/CTE for control of Environmental Pollution from industries. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.27 | Improved Combustion technology | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.28 | Implementation of SOx and NOx standards notified by MOEF&CC | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.29 | Prepare and implement local area action plan for pollution hotspots and strict enforcement of air pollution control measures in all industries, including those located in unauthorized areas. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.30 | Assess the number of industrial units that are non-compliant and prepare unit/plant wise action plan for time bound compliance or be shut down. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.31 | Carry out pollution load estimation from industrial sector to enable setting of target for emission | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP1.32 | Industrial units to install water spraying system of internal roads and washing of tyres of vehicles | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
|  | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP2 | Material Storage and handling in industrial
IP2.1 | Industry should Store and handle all A class petroleum products & Solvents in the tanks having floating roof. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP2.2 | Industry should devise time bound plan, to switch over the existing A class solvent storage from fixed roof to floating roof | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP2.3 | Styrene, Xylene (Class-B) should be stored and handled similar to class-A products considering their concentrations in the atmosphere. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP2.4 | All Floating roof tanks should be provided with double seals with suitable preventive maintenance procedure in place for seals to maintain the sealing efficiency. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP2.5 | Industry should evolve an internal monitoring system for cleaning of major tanks of Class-A & others (Styrene and Xylene), which may include supervision of cleaning activity by representative of Environment dept. of respective industry. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP2.6 | Industry may also evolve a system of work-zone VOC monitoring pre and post cleaning of tank. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP2.7 | Industry should devise time bound plan, to switch over the existing tanker filling from top filling to bottom filling | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP2.8 | Industry should evaluate the existing facility or Design new facility for the suction of fumes/ solvents vapours during tanker filling operation from technically competent agency for efficient handling of fugitive emissions. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP2.9 | Industry should identify the sources of low potential emission rate and plan the suitable adsorption / absorption system for vapour treatment. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
|  | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP3 | OCEMS in Industries
IP3.1 | There should be provision to use CEMS data as legal evidence and a policy be framed in consultation with Central Pollution Control Board. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP3.2 | Implement Continuous Emission Monitoring System (CEMS) across all targeted and applicable polluting industry | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP3.3 | Development of mobile facility/van for continuous ambient air quality monitoring for different localities. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP3.4 | Live camera feed and to take action against non-complying industrial units | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
|  | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP4 | Clean fuel in industries
IP4.1 | Introduction and shifting towards cleaner fuels in industries | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP4.2 | Conversion to CNG/PNG from pet coke /wood / coal and urgent ban on furnace oil, pet coke, which are dirty industrial fuels with high sulphur and heavy metals | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP4.3 | Strict enforcement against illegal use of such fuels, including fuels which do not have specifications laid down or are included in the acceptable fuels as mandated by state pollution control boards | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP4.4 | Establish a protocol for using cleaner fuels & technology in industries | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP4.5 | Restriction on using un-authorised fuels in industries | Implemented |  | 2023-03-01 |  |  | Yes | [6 empty] | Approved fuel where Biomass, wood & coke are allowed. Pet coke and Furnace Oil for the new units are restricted. Roots and chipped material from plyboard industries are allowed
IP4.6 | Sulphur reduction in fuel | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP4.7 | Alternate fuel- Hotel industry directed to change fuel patten from HSD to Natural Gas. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP5 | Control of air pollution from Brick kilns
IP5.1 | Adapting new technologies for Brick kilns | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP5.2 | identification of brick kilns and their regular monitoring including use of designated fuel and closure of unauthorized units. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP5.3 | Conversion of natural draft brick kilns to Force/ induced draft. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP5.4 | Closure of unauthorized units by seeking the possibility for shifting of kilns outside corporation limits | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP5.5 | Prescribe design specifications for improved kilns and ensure compliance checking to know that conversion has actually taken place. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP6 | Control of air pollution from Thermal Power Plants and coal handling units
IP6.1 | Regular audit of stack emissionsfor QA/QC | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP6.2 | Sprinkling arrangements at Siding/Permanent Transportation routes/Coal Dumps | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP6.3 | The covering of loaded transport vehicles will be compulsory in TPP and coke units | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP6.4 | All haul roads will be made pucca, by. New haul roads will be taken in use after making it pucca | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP6.5 | All ash dumps will be enclosed by pucca boundary to prevent entry through them. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP6.6 | All processing of ash will be done in covered space. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP6.7 | The chimneys of all boilers will be equipped with ESPs with on line monitoring systems. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP6.8 | Dry ash collection system shall be installed and dry ash sale cement mills shall be resumed. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP6.9 | All ash shall be disposed of by utilization or sale and it will be continued from. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP6.10 | The plantation of saplings for creation of tree and forest cover of local species in TPP | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP6.11 | The conversion of abandoned / inoperative mines into water bodies. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP6.12 | The space of processing of coal or coke will be kept covered in coke units. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP6.13 | Sulphur reduction in fuel by using low sulhur content Imported coal in Thermal Power plant. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP6.14 | Installation/ up gradation of air pollution control systems in Thermal and Petrochemical industries. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP6.15 | Use of high grade coal made compulsory in thermal power plant. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP6.16 | Action plan to address emissions from thermal power plant by installing FGD plant | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP6.17 | Implementation of new thermal power plant standards in all powerplants | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP6.18 | Check status of compliance and prepare a transition plan for each power plant to meet the new standards | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP6.19 | Plants found not meeting set emission reduction targets to be penalized | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP6.20 | Chart a roadmap for cleaner plants and Incentivize their operation by giving them the priority over other polluting plants | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP6.21 | Adopting cleaner technology in coal based thermal power plants | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP6.22 | Switching to power generation from existing wind and solar plants (renewable source) to reduce operation of coal based power plants | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP6.23 | Permanent closure of old TPP or move towards cleaner natural gas. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP7 | Control of air pollution from Coke ovens
IP7.1 | Coal fired boilers to be converted to oil/gas fired driers, preferably with coal bed methane (CBM) | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP7.2 | Switch to coke dry quenching system (CDQ) | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP7.3 | Increasing carbonization chamber height | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP7.4 | High pressure ammonia liquor aspiration | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP7.5 | Wet oxidative desulphurization of coke oven gas | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP7.6 | Stationary land-based pushing emission control | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP8 | Control of fugitive emissions in industries
IP8.1 | Use of hoods and enclosure for all process equipment, hooding of emission controls of the blast furnace tapping operations and discharge of molten metal and slag, covering of ladles containing molten metal | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP8.2 | Scrap management programme for the prevention or minimization of contaminants in steel scrap and other feed materials | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP8.3 | Use of covered or enclosed conveyors and transfer points | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP8.4 | Enclosures for emission controls of the charging and tapping operations . | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP8.5 | Minimising the number of flanges by welding piping connections wherever possible and using appropriate sealing for flanges and valves | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP8.6 | Wet quenching of coke as opposed to conventional quenching | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP8.7 | Use of larger oven chambers and regulation of pressure within oven chambers | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP9 | Control of air pollution from Iron and Steel industry:
IP9.1 | Use of desulphurized coal | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP9.2 | Use of pulverized coal injection method | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP9.3 | Installation of coke dry quenching (CDQ) | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP9.4 | Installation of top gas recovery Turbine (TRT) | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP9.5 | Introduction of coal dust injection (CDI) | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP9.6 | Introduction of coal dust injection (CDI); waste heat recovery in Sinter Plant; waste heat recovery at blast furnace stove | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP9.7 | Use of byproduct fuel for power generation | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP9.8 | Waste heat recovery in Sinter Plant; Waste heat recovery at blast furnace stove | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP9.9 | Switch to Direct Reduction Electric Arc Furnace from basic oxygen furnace | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP9.10 | Upgradation of Air Pollution Control System | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP10 | Control of air pollution from mining area
IP10.1 | Maintenance of mine area roads | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP10.2 | Greenbelt for activity zone and the buffer zone for each mining area | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP10.3 | Effort for good mining practices | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP10.4 | Control of fugitive emission in Open Cast Mine by use of mechanized sweeping machine, long range fogging machine. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP11 | Control of air pollution from generator sets
IP11.1 | Allow only DG sets meeting emission and design of chimney/ exhaust, acoustic enclosures standards to operate | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP11.2 | Curtail use of DG Sets in social events by providing temporary electric connections | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP11.3 | Ensure access to quality electricity supply | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP11.4 | Discourage use of DG sets in cellular towers. Promote use of alternate power | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP11.5 | Levarage rooftop solar programme to reduce dependance on DG sets | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP12 | Control of air pollution from waste incineration
IP12.1 | Strong siting policy for Waste to Energy Plants | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP12.2 | Strong siting policy for Biomedical Incineration Plants | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP12.2 | Implement CEMS for incinerators and provide data on emissions on an open platform | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
|  | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP13 | Renewable Energy
IP13.1 | Link energy requirments for solar power plants to shift to zero emission target | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP13.2 | Identify and target commercial and industrial establishments for installation of roof top solar system | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP13.3 | Identify canals and open spaces for installation of solar systems | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
IP13.4 | Organise consumer outreach programme for roof top solar programme | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
*AP1.2 | Installation and operation of advance air pollution control systems and Continuous Ambient Air Quality Monitoring System in Industries located in and around Kashipur and at M/s Hindustan National Glass Industries Ltd, Rishikesh | In Progress |  | 2023-03-01 |  |  | Yes |  | Nil | Nil | Nil | NA | NA | Industry Association represented that despite of establishing individual CAAQMS, it will be appropriate to place 01 CAAQMS at Central of the city. Because, the purpose of CAAQMS is to see the status of air quality and as per CPCB guideline, 01 CAAQMS is to be installed in the city having population 1-5 lakh. This matter was considered in a meeting chaired by Member Secretary with Industry Association, and decided that the Industry Association will establish such station in the City. UKPCB has published Tender for procurement of 01 CAAQMS for Kashipur.
*AP1.4 | Compliance of guidelines on D.G. sets regarding use of retrofitted emission control system (PM captured efficiency 70%) capacity equal to or above 800 KW (for both cities) | Completed |  | 2021-03-01 |  |  | Yes |  | Nil | Nil | Nil | NA | NA | As per Regional officer information, all the DG sets are fitted with the retrofitted emission control system
*AP1.5 | Removal of Open DG sets (for both cities) | In Progress |  | 2023-03-01 |  |  | Yes |  | Nil | Nil | Nil | NA | NA | As per report of ULB there are total 375 DG sets in the city out of which 234 DG sets are operating illegally. ULB is being asked to submit status of such DG sets with their capacity and what non-compliance is made (for the support of statement illegally operated) All wedding halls, banquet halls are advised not to use the open DG sets. As per report of Regional Officer, Kashipur dated 31.08.2020, 06 DG sets in Kashipur are operating without acoustic enclosures. SDM Kashipur has been directed to seal such DG sets.

## Waste &Biomass
WASTE AND BIOMASS- DUMPING AND BURNING
BB1 | Biomass Burning | Present Status | Target | Target Date | Deviation from Approved Action Plan Target | Annual Target | Field type | Attachment | Attachment Contents | Total Funds Allocated | Funds released | Funds Utilized | Additional Funds Required (in Lac) | Remarks
BB1.1 | Regular check and control of burning of municipal solid wastes | In progress |  |  |  |  | Yes |  |  |  | Nil | Nil | Nil | Government of Uttarakhand has issued order on 29.12.2019 for imposing Penalty of Rs 5000/- per violation. It is prohibited and there is provision of fine as per the Gazette notification and SWM Rules, 2016.
BB1.2 | Defaulters for open burning to be imposed fines | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
BB1.3 | Identify Garbage burning locations and | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
BB1.4 | Prohibition/complete ban on garbage burning. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
BB1.5 | Launch extensive drive against open burning of bio-mass, crop residue, garbage, leaves, etc. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
BB1.6 | Construction of advanced waste management Site. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
BB1.7 | Regular collection and control of municipal solid wastes. | In progress |  | 2021-03-01 |  |  | Yes |  |  |  | Nil | Nil |  | 1. A total of 54 MTD Waste is generated. 2. ULB has achieved almost 100% Door to Door Collection of Waste. It is done by 2 teams of 20 workers in each.
BB1.8 | Providing Organic Waste Compost machines , decentralization of processing of Waste, dry waste collection centers. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
BB1.9 | Awareness for controlling of burning of agricultural waste and crop residues. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
BB1.10 | No plot should be left open more than 02 years and planting of trees must be mandatory on vacant plots. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
BB1.11 | Dead Bodies of Animals should be disposed through proper treatment facility like rendering plant etc | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
BB2 | Ensure segregation of waste at source | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
BB3 | Proper collection of Horticulture waste and its disposal following composting-cumgardening approach | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
BB4 | Recycling plants for dry waste. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
BB5 | Ambient air quality monitoring of municipal dumping sites and parks | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
BB6 | Check/stop on Stubble Burning | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
BB7 | Action plan to minimize the forest fire | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
BB8 | Use of Piped Natural Gas (PNG) for Human cremation. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
BB9 | Use of satellite based monitoring as well as mobile spot check squads for enforcement | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
BB10 | Landfill fire | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
BB10.1 | Proper management of landfill sites to prevent spontaneous fire | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
BB10.2 | Adopt roadmap for zero landfill policy to promote decentralized waste segregation, reuse and recycling | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
BB11 | Fire crackers—regulate to control their usage | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
|  | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
DF1 | Domestic Fuel | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
DF1.1 | Increasing the LPG connections in low income strata. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
DF1.2 | Ensuring promotion and use of cleaner fuel (i.e. LPG) instead of coal fired chulas or fire-woods in the hotels and open spaces | Implemented |  | 2023-03-01 |  |  | Yes |  |  | 40 | 0 | 0 | 40 | PNG is now available in Kashipur. Presently 03 Industries are using LPG / PNG. Due to covid-19 Dhaba / Eateries are less in numbers and all are using commercial LPG cylinders.
DF1.3 | Introduce schemes for providing subsidized LPG connections as well as providing means of finance to small tea vendors/hawkers using kerosene stoves in order to reduce emissions from burning of kerosene | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
DF1.4 | To mandate LPG/Bio gas in commercial eateries. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
DF1.5 | Ensuring 100% electrification and uninterrupted electric supply with in the city. | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
DF1.6 | Ensure easy availability of affordable cleaner cooking fuels (LPG in urban areas & biogas in rural areas) | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
DF1.7 | Introduction of improved chullahs (low emission chullahs) | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
DF1.8 | Implementation of Pradhan Mantri Ujjwala Yojana (PMUY) | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
DF1.9 | Shift to LPG from solid fuel & kerosene for domestic applications | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
DF1.10 | Use of LPG in Bakeries | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
DF1.11 | Adopting Better construction practices with PM reduction of 50% | Nil | Nil | Nil | Nil | Nil | Nil |  | Nil | Nil | Nil | NA | NA | Not incorporated in the Action Plan
*AP1.3 | Pilot Project on making Agriculture waste residue to Fire Briquettes (for Kashipur Only) |  |  | 2021-03-01 |  |  | yes | [6 empty] | Agriculture department is proposing to give funds for setting up Straw bailing machines. In Kashipur area this will cost about Rs. 40.00 lakhs funds to be given to farmers for the same. For Financial aid proposal is to be received through Directorate.
[10 empty] | 40 | 0 | 0 | 40

## Air Quality Data
AIR QUALITY DATA
Action Code | Action Point | Field type | Attachment | Attachment Contents
AQ1.1 | Monthly averages for PM2.5 (In µg/m3) | 207.85 | NA | NA
AQ1.2 | Monthly averages for PM10 (In µg/m3) | 122.15 | NA | NA
AQ1.3 | Monthly averages for SO2 (In µg/m3) | 18.62 | NA | NA
AQ1.4 | Monthly averages for NO2 (In µg/m3) | 23.94 | NA | NA
AQ1.5 | Annual averages for PM2.5 (In µg/m3) | NA | NA | NA
AQ1.6 | Annual averages for PM10 (In µg/m3) (Jan-Nov 2020) | 116.94 | NA | NA
AQ1.7 | Annual averages for SO2 (In µg/m3) (Jan-Nov 2020) | 12.07 | NA | NA
AQ1.8 | Annual averages for NO2 (In µg/m3) (Jan-Nov 2020) | 18.06 | NA | NA
AQ1.9 | Monthly Meterological Data | NA | NA | NA